# PILOTING

# QUANTIFIED PARTICIPATORY ASSESSMENTS

# IN DPIP (RAJASTHAN)

## FINAL REPORT

A. J. James 1 and Rakesh Kaushik2

March 2002

2 Director (Development Support)

NODES (Nodal Organisation for Development Enterprise Support)

At MBCC,   SCO 333-34, Sector 35-B

Chandigarh 160 022

Tel: 	(01762) 31241 (residence)

(0172) 600 532/533 (messages)

Fax: 	(0172) 600 531

Email: 	drkaushik@vsnl.com

1 Environmental & Natural Resource Economist

B 9 First Floor, South Extension  Part 2

New Delhi 110 049

Tel: 		(0124) 895 1338

Fax:	  	(011) 625 8006

Email: 	   	ajjames@vsnl.net

# CONTENTS

- Overview: Piloting QPA in DPIP

- Project Objectives, Processes and Procedures

- QPA Pilot: Activities and Outputs

- QPA in Process Monitoring

Annex 1:  	Pilot QPA Formats

Annex 2:	QPA Pilot in Dausa and Churu Districts: Main Findings

Annex 3:	QPA in Churu: Main Findings

ABBREVIATIONS

APP		Anti Poverty Programmes

BC		Block Coordinator

CF		Community Facilitator

CIF		Community Investment Fund

DFID		Department for International Development, Government of UK

DPC		District Project Coordinator

DPIP		District Poverty Initiatives Project

DPM		District Project Manager

DPMU		District Project Management Unit

DTT		District Training Teams

GO		Government organisations

GoI		Government of India

GoR		Government of Rajasthan

LD		Line Department

MPA		Methodology for Participatory Assessment

NGO		Non-governmental organisations

PAD		Project Appraisal Document

PIP		Project Implementation Plan

PRIs		Panchayati Raj Institutions

QPA		Quantified Participatory Assessment

SPD		State Project Director

SPMU		State Project Management Unit

VDA		Village Development Agency

1. PILOTING QPA IN DPIP

  - QUANTIFIED PARTICIPATORY ASSESSMENTS (QPA)

Quantified Participatory Assessment or QPA is a methodology that uses a variety of participatory and other methods to collect information from project stakeholders. A distinctive feature is the collection of qualitative information in quantitative form, which helps integrate qualitative information with regular MIS data, to give project management an integrated view of project performance alongside financial and physical data. In addition, the methodology can provide timely information of field level problems for corrective action by project management. The methodology is flexible and can be adapted to suit the information needs of each project, especially qualitative issues at the field level.

The origins of the QPA are in the MPA or Methodology for Participatory Assessment, developed by a multi-disciplinary team working on the Participatory Learning and Action (PLA) study, funded by the Water and Sanitation Program (WSP), which evaluated the sustainability of 88 water and sanitation projects in 15 countries (Gross, van Wijk and Mukherjee (2001)). Brief summaries of the main points of this methodology are James (2001) and James (2000a).

The QPA is a more flexible methodology, which can be used to assess issues other than sustainability (the focus of the MPA). Like the MPA it uses a descriptive ordinal scoring system to capture qualitative information in terms of numbers, but it also uses a variety of other methods to collect information, including survey methods, non-descriptive scoring systems, indices of change and cardinal measurements (see James et al., 2002).  Unlike the MPA, however, the QPA is a rapid assessment, which makes it cost-effective and appropriate for large projects. The methodology was applied in 2000 to a watershed context to assess the socio-economic and environmental impact of an EC-funded watershed project in Dehradun, India (James (2000b)), and has also been used in the assessment of qualitative issues in the Water Resource Audit of the on-going Andhra Pradesh Rural Livelihoods Project (APRLP), funded by the Department of International Development (DFID), Government of UK (James, 2002a and 2002b).

Applying the QPA to the DPIP in Rajasthan was discussed in an earlier report (James & Kaushik, 2000). This pilot was carried out in the districts of Dausa and Churu during July – October 2001.

  - THE QPA PILOT IN DPIP

1.2.1	The Approach

The pilot study is to demonstrate the utility of the QPA to the project, with all the output being aimed at illustrating the nature of analysis rather on pre-determining what the project should do. Based on the demonstration, project management can decide what information to collect. The approach sought to keep the assessment itself simple, since Community Facilitators (CFs) were to implement the QPA with village level Common Interest Groups (CIGs).

    - Objective and Focus

The overall objective is to pilot an institutional structure that will

- Collect qualitative and quantitative information on project implementation at village, district and state levels,

- Bring different stakeholders together to discuss this information, and

- Feed into project decision-making for improved performance in future.

Although systems like the Performance Tracking System and the Financial Management System do collect village-level project information, the QPA pilot focused on qualitative issues of project processes at the village level. In particular, seven specific processes were identified for assessment:

- Awareness generation

- Formation of a common interest group (CIG)

- Preparation of sub-project proposals

- Group development

- Capacity building

- Participation in decision-making, and

- Transparency

These are described in greater detail in section 2.

1.2.3	Developing QPA Formats

Three village visits were made to pre-test the QPA formats originally designed for the CIG assessments. Two visits were made during the first round of pre-testing in Dausa during early August 2001 – to Khawarauja village and Charada village – while the second round of pre-testing was carried out in Kodar Tal village in Churu district in September 2001. All pre-tests were done with CFs and BCs of the districts. The final QPA format used in the village assessments is in Annex 1.

    - Structure and Coverage

The pilot study was carried out in 4 villages in Lalsot block of Dausa district and 4 villages in Ratangarh block of Churu district. It had three parts, (1) village-level assessments, (2) district level assessments and stakeholder meetings and (3) state-level assessments and stakeholder meetings.

Table 1.1: Coverage of Village and District-level Assessments

| Level | Activity | Coverage |  |
| --- | --- | --- | --- |
|  |  | Dausa district | Churu district |
| Village | Assessments | Kushapura | Mollesar |
|  |  | Nichuniyan | Ghumanda & Bachrara |
|  |  | Sindoli | Daudsar |
|  |  | Kanwarpura | Gorisar |
| District | Assessments | Community Facilitators (CFs) | Community Facilitators (CFs) |
|  |  | Block coordinators (BCs) | Block coordinators (BCs) |
|  |  | District Project Coordinator (DPC) and staff | District Project Coordinator (DPC) & staff |
|  |  | District Project Manager (DPM) and DPMU staff | District Project Manager (DPM) & DPMU staff |
|  | Stakeholder meetings | CFs, BCs, DPC & staff, DPM & DPMU staff, Collector, banking sector representatives | CFs, BCs, DPC & staff, DPM & DPMU staff, Collector, banking sector representatives |

At the state level, discussions were held with the training institutions and the State Project Management Unit (SPMU), where the main issues raised at the district stakeholder meetings were presented. Finally, a state-level stakeholder meeting brought together stakeholders from the two districts and the SPMU. Activity at all levels was coordinated and facilitated by the World Bank consultants.

1.2.4	Village Level Assessment

Nature of information collected

Village-level assessments sought to collect three types of information from members of CIGs and  from other village leaders.

- Qualitative information for ordinal scoring on the extent to which project processes were being implemented in the field (the main focus)

- Details of the proposed sub-project as understood by the group

- Secondary information from villager leaders on issues relating to demography and current access to social and economic infrastructure, to update available secondary information.

Other Qualitative issues: In addition to the above, members of the assessment team recorded observations, comments and suggestions by the CIG and others during the village visit. A short summary of the village visit, including these qualitative issues, was prepared in Hindi, translated into English and filed into a Village File. These comments give further information to understand and explain the QPA scores given for each CIG assessed.

The ordinal scoring of the qualitative responses from village level assessments was done by the CFs and BCs along with the facilitators, during the extensive de-briefing on the day after each village visit.

Logistics

Village level assessments of CIG functioning (processes and sub-projects) and the collection of secondary information was done by Community Facilitators (CFs) from adjoining villages and BCs were trained to conduct the assessment in 4 selected villages in each district. There were 2 assessment teams, comprising 4 CFs, 1 BC and a World Bank consultant.

Village visits were completed at a rate of one village per day per team, including a 2-hour meeting with the village leaders (to collect secondary information), and 1-2 hour meetings with a maximum of 4 CIGs per village. The ordinal scoring of the QPA questions was completed during the debriefing the next morning.

Debriefing

Each village assessment was followed by a short debriefing session the following morning. A 2-page Hindi version of the village report, containing relevant observations from the field visit and also key details of the CIG activity, was prepared beforehand and discussed during the debriefing. Also, team members read out and discussed the QPA scores from each CIG. The purpose of the debriefing was to add details missed by the author(s) of the report, and to make necessary modifications to the views and scores, based on a collective understanding of the issues involved. The focus of the discussions remained the ordinal score and the reasons given for each score. At the end of the morning, the finalised QPA format sheet and village report was ready to be entered and stored.

Data Entry and Data Storage

This information is stored in a community folder in the NGO’s office. This information, in an appropriate form, could also be given back to the CIGs. Each community folder contains

- The completed QPA formats for each CIG in a habitation

- A brief (2 page) village report in Hindi, containing observations from the field

- Details of the CIG sub-project proposed

- A copy of the original PRA report for the village

1.2.5	District Level Assessment

There were two types of district level activities: (1) individual assessments of district level stakeholders and (2) a district-level stakeholder meeting to discuss issues raised during village-level assessments and district-level assessments.

Individual Stakeholder Assessments

District level assessments were done for CFs, BCs, DPCs and staff, and for DPMs and DPMU staff. These covered issues ranging from the nature of support they received from other project stakeholders, the nature of capacity building, problems faced and suggestions for improvement.

Stakeholder Meet

District-level stakeholder meetings lasted about half a day and were attended by a few CFs, the BCs, the DPCs and their staff, the DPM and their staff and the Collector (or his representative) and banking sector representatives working in the district. These meetings discussed the village assessment scores and the reasons for the scores, and sought to resolve issues that could be resolved at the district level. But issues that needed state-level action were identified and flagged.

The consultants prepared a short report of the issues discussed, for presentation at the state-level stakeholders meeting.

Logistics

The district-level assessments consisted of 2-3 hour meetings with (1) the CFs, (2) the BCs, (3) the DPC and his staff, and (4) the DPM and the DPMU staff. These were a mix of ordinal scoring and open questions and took one full day to complete.

The district stakeholder meeting took half a day.

Thus, 4 village assessments, individual stakeholder assessments and a stakeholder meeting were completed in a 6-day week. Needless to say, this was possible because all arrangements are made beforehand, the assessment teams are trained and ready, the villagers had been informed, the NGO and DPMU were prepared and ready, and invitations had been sent to bankers and concerned government officials to attend the stakeholder meeting.

    - State Level Assessment

There were two types of state level activities as well: (1) assessments of issues with the staff of the institutions involved in training, IGPR&GVS and Aravali, and with the SPM and the SPMU staff; and (2) a state-level stakeholder meeting to discuss, along with the district representatives, issues raised from the district-level stakeholder meetings, and to chalk out a time-bound action plan for their resolution. The assessments took half a day each, as did the state-level stakeholder meeting.

1.2.7	Project Information Flows

The QPA aimed to provide an institutional structure to facilitate improved flow of information between the village, district and state-levels of project operation. While information does flow from one level to another, an institutional structure that allows all stakeholders to voice their concerns  and offer suggestions, augments these flows of information. The quicker project management gets to know about problems and the more suggestions that are offered to resolve issues, the better is the implementation of the project.  These assessments, therefore, are not meant to be faultfinding exercises, but a means to improve communication between different stakeholders in the project, and to effect course-corrections to improve future project performance.

Two types of information flows were targeted: (1) self-learning, through reviews and discussions with the facilitators; and (2) identification of core issues hampering better project implementation, and suggestions for improvement. Core issues that could not be solved at the district level stakeholder meetings were taken up at the state level.

Figure 1.1 is  a schematic description of information flows facilitated by the QPA.

Figure 1 : Information Flows facilitated by the QPA

CIGs

Village Level

Self-learning

Issues and their resolution

SPMU

DPMU

NGO

Training Institutions

District Level

State Level

2. ASSESSING DPIP PROCESSESES

  - INTRODUCTION

The QPA pilot aimed to assess the extent to which seven key project processes are being followed on the ground seven key project processes. There is a distinction between processes and procedures, which became clear on reading the three main project documents dealing with processes: the Project Appraisal Document (PAD) of 31 March 2000, the Project Implementation Plan (PIP) of February 2000 and the Project Guidelines (in Hindi) issued in March 2001. Since there were differences between these three documents, the PAD was taken as the guideline for preparing the formats of the QPA.

This section begins by linking objectives to processes, and then describes the QPA questions designed to assess the extent to which these processes were being followed on the ground.

  - PROJECT OBJECTIVES AND PROCESSES

Goals, aims and objectives specify what is to be achieved, while processes essentially describe how these are to be achieved. Assessing project processes, therefore, requires a clear understanding of what the project is aiming to do. The PAD sets out the following:

Long-term goal: 		Reduction of poverty in selected districts.

Development Objectives: 	To improve the economic opportunities, living standards and the social status of the poor in selected villages of these districts.

Specific objectives:

- Mobilize and empower the poor and help them to develop strong grassroots organisations that facilitate access to and participation in democratic and development processes.

- Support small-scale sub-projects that are priorities chosen, planned and implemented by the poor.

- Expand the involvement of the poor in economic activities by improving their capacities, skills, access to social and economic infrastructure and services, and employment opportunities

- Improve the abilities of non-government, government and elected government (PR) institutions to hear, reach and serve poor clients, i.e., to function in a more inclusive and participatory manner.

Since the last specific objective refers to influencing the working of NGOs, GOs and PRIs, the processes leading to the fulfilment of this objective were not considered for the pilot.

The first three specific objectives imply that group formation, awareness generation and training are only means to an end. What really matters is whether the poor are empowered enough to access and participate in community decision-making and development programmes. This suggests a gradation of effort, which is characterised below.

Level One Activities 	that aim to mobilise the poor, form them into groups, improve their capacities and skills, and help them choose and plan small-scale sub-projects.

Level Two Activities 	which aim to increase the participation of the poor in economic activities, improve access to and participation in democratic and development processes, etc., and

Level Three Activities	 that aim to improve the economic opportunities, living standards and the social status of the poor.

This further suggests a phasing over time for the achievements of these objectives, which in turn helps define assessment indicators that are relevant at different points of the project cycle.

Finally, and perhaps most importantly, these objectives clarify the purpose of group formation beyond merely applying for and receiving sub-project funds. If the objective is to form self-reliant groups at the village level, capable of accessing formal bank credit and government schemes, and of participating as equals in community decision making, it implies certain processes that need to be followed in forming and developing groups.

2.2	PROCESSES AND PROCEDURES

The Guidelines for Project Implementation describe procedures to be followed at different levels (but focusing on the CFs and CIGs). These procedures are to implement project activities (e.g., group formation, sub-project application, evaluation and implementation) and should be distinguished from project processes.

To illustrate, the activity of ‘group formation’ has a set of procedures laid down in the Guidelines (which specify who can be part of a group, how non-BPL members can be inducted, how many copies of the resolution have to be made, when the bank account is to be opened, etc.). But the process of forming a group has much more – including awareness generation - which is distinct from the procedure of conducting an awareness generation programme (e.g., beating a drum, having banners, distributing pamphlets, holding a meeting, etc.), discussing possibilities and problems with group members, going around to identify the poor with common interests, etc.

Similarly, the process of building a group after it has been formed, has to be done with the objective of empowering the poor so that they ‘develop strong grassroots organisations that facilitate access to and participation in democratic and development processes.’ This requires a process of working with the group, responding to their needs, supporting their efforts, tackling the problems they face, providing information, etc.

Assessing project processes, thus, needs to go far beyond merely checking procedures.

#### 2.3	KEY PROCESSES TO ACHIEVE OBJECTIVES: SOME OBSERVATIONS

2.3.1	Constraints to Improving Group Incomes

Adverse pre-conditions can constrain the effectiveness of investment in group formation and development, and hence, achievement of project objectives of reducing poverty. These pre-conditions may be of two kinds:

- Area-based: Since some of the poor are so because the area and the resources are poor, these could limit the effectiveness of project investment. Roads, public transport, electricity, piped water supplies and veterinary services are important infrastructural constraints on effective utilisation of project investment by the poor. Since not all of these can be addressed directly by the project (e.g., electricity), there may, thus, be an argument for tackling these constraints at least simultaneously, if not before investments are made at the village level.

- People-based: The poor are also illiterate, discriminated, abused, disabled, uninformed, fearful and tend to have low levels of self-esteem, self-belief and self-confidence and indeed, confidence in the government system. It is therefore going to be much more difficult to mobilise the poor, which means that the CFs are going to have to invest time and effort into this process. One way is to do group formation in phases, so that the success of one group can be demonstrated to mobilise further groups. This, however, has implications for project phasing, implying that at least 3 years are required per village (or habitation), in which case the situation of habitations taken up in the last year of official project implementation (i.e., 2005) will have to be re-examined.

Satisfying these pre-conditions will improve the effectiveness of project investment – which will be captured in the evaluation of project processes – while failing to tackle them soon may lead to ineffective investment.

    - Addressing Wider Sectoral Issues

A lot of the ‘sectoral issues’ slated in the PAD to be addressed by the project require much wider influence than the rest of the project description entails. Visualising ‘spheres of influence’ as concentric circles, the project has greatest influence within its own geographical, financial, and administrative domain. The next circle is that of the department of rural development, which handles many more areas of direct relevance to poverty alleviation (e.g., drinking water supply, government APPs, watershed programmes, etc.), but the SPMU has presumably less influence in this sphere than in its own domain. Finally, the success of the project in addressing sectoral issues depend on the extent to which other major departments like agriculture, irrigation, rural electrification, roads, etc. are able to support the micro-level engagement of DPIP. This is the third circle, where the influence of the SPMU is arguably the lowest.

A similar case may be made out at the district level, where outside the DPMU, the next circle includes the DPCC, where line departments are members, and the PRIs, and the last circle includes financial institutions, commission agents, market access, transport networks, etc.

Since the performance of these two outer circles can have critical impacts on the performance of DPIP, it is important that the project begin to work on these links as soon as possible.

The DPIP objective of improving PRI performance is not only important in itself (to facilitate groups’ access to development programmes), but also important in ensuring the success of investments made from the CIF – which, in turn, has a major effect on the overall objective of improving the economic opportunities, living standards and social status of the poor.

    - Effective Services from Infrastructure

From past experience, it is clear that simply providing infrastructure (e.g., health centres, hand pumps, even roads) is not enough to ensure a flow of services from the infrastructure provided; regular staff, funds for O&M, and individual or institutional responsibility are also required. Project processes have to ensure that sub-projects to build social infrastructure address this wider set of concerns, in addition to merely providing funds to build the infrastructure and ensuring good quality construction with equitable contributions across poor and non-poor households in the villages.

    - Promoting Viable Micro-enterprises

The track record of micro-enterprise promotion to alleviate rural poverty is not a good one. Among the factors mentioned are the low incomes produced by low quality output from low skill using traditional enterprises (e.g., basket weaving, leaf plate pressing, bindi and agarbatti manufacture, etc.), the difficulties of accessing markets (to poor suppliers who are not well-versed with market structures and procedures), conflict of interest with established middlemen, adverse impacts of market price fluctuations, and problems of scale and quality control.

Promotion of micro-enterprises by development programs has generally involved only conducting training and providing assets and working capital (if at all). There has been little effort to equip a group of trainees to function as a group of entrepreneurs. Added to this is the reluctance of many of the poor to go in for micro-enterprises; they would rather have a ‘job’ that would earn then ‘wages’. This is for a variety of reasons ranging from the lack of traditional knowledge and support to do entrepreneurial activity (as opposed to traditional trading or entrepreneurial families), to inability to bear production and market risks.

It is vital, therefore, that the process of developing micro-enterprises in the project not be restricted to granting funds (from the CIF) to groups, who may only have been token signatories to the sub-project proposal in the first place.

The process of developing micro-enterprises has to include setting up a much wider support system, which provides constant guidance and information to see the micro-enterprise group through the initial stages to self-reliant performance at the end of the project’s involvement. This will involve providing

  - guidance on the choice of product/activity, technology, pricing, market choice, transportation, cost cutting options, formation of guilds or societies, etc.,

  - information on competing products and competitors, market prices, new technology and newer markets

  - beside the basic skills of account keeping, planning of future output and investment in capital, conflict resolution, functioning .

    - Addressing Gender Concerns

Women are an important section of the poor, given that they have the responsibility of bringing up children, feeding the family, looking after the sick, the aged and the disabled, bringing drinking water, cleaning the house, taking care of sanitation and hygiene, and looking after animals and kitchen gardens. Often, they are also involved in small-scale micro-enterprises (like basket making, bindi making, agarbatti etc.). All of these are activities that the project seeks to affect.

While qualitative indicators can capture the extent to which women are able to participate in the project, the more important aspect is the nature of the process being followed on the ground to involve women more meaningfully in the project.

Merely checking the extent to which women ‘enlist’ in the project – i.e., the number of women CIGs formed or women participating in CIGs - says little about the nature of women’s participation or the support being given to them to participate in and benefit from the project. While it is true that, given the abysmal state of women’s development in the state, even enlisting women in project implementation is a major advance, the project needs to do much more if it has to achieve the objective of improving the ‘access to and participation [of the poor] in democratic and development processes’.

Special support processes (i.e.,  in addition to those for viable micro-enterprises and effective infrastructural services) for women’s involvement in project activities would include

- making special efforts to inform women about project processes and meetings (since they are often not able to attend community meetings, and are often not able to read printed pamphlets),

- holding meetings at times and places that are convenient for them to attend (since women have tight working schedules to collect water, fuel wood, fodder, and to cook meals for the family, do the household chores and look after elders in the house – and ignoring any of these could invite rebuke from husbands and male family members, which could deter their further participation in the project)

- persuading husbands and males in the family to allow women to go for training even outside the village, and organising women to go along with groups of other women

- ensuring that women have some control over earnings from micro-enterprises (e.g.,. opening separate bank accounts for women)

- organising support groups for women within the village, which are able to meet and offer a joint front in cases of conflicts, especially with men in the family or the village.

All the above are features of a process to involve women meaningfully into the project which, if not done properly, can restrict the participation of women and hence the extent to which they derive benefits from the project.

    - Building Transparency And Accountability Into Project Implementation

Providing information to increase awareness among project stakeholders about issues addressed by the project (e.g., the need to pay serious attention to hygiene, sanitation, and women’s education) and to promote effective participation in project procedures, benefits, status of activity and financial details, are as important to sustaining project benefits as the investment of funds in community infrastructure and micro-enterprise development.

Increased awareness of project principles and approaches is also vital to enlist the effective participation of poor men and women, who are also afflicted by the concomitants of poverty, including illiteracy, ill health, disability, indebtedness, discrimination by upper castes and upper classes, low self-esteem, lack of confidence and motivation. As noted earlier, special efforts have to be made to motivate them enough to participate effectively in the project. A critical component of that effort – and indeed the process underlying the effort – is to communicate effectively with these stakeholders.

While providing information to project stakeholders is undoubtedly a vital component of effective implementation, it is essential to move beyond checking whether or not an announcement was made in the gram sabha or whether pamphlets were distributed. It is perhaps more important to ensure that the recipients received the information and understood its implications. Special processes may have to be used, beyond the normal communication tools of beating drums, keeping meeting minutes and making public announcements, to ensure that the poor involved in the project – even the illiterate - are kept informed of project-related events.

Keeping the primary stakeholders, namely, the members of the CIGs, informed of project progress is also crucial to ensuring transparency and accountability in implementation. Processes to ensure transparency and accountability, thus, have to include provisions for

- public display of project progress (e.g., painted boards displayed outside buildings, which are  regularly updated),

- regular reading of financial accounts and bank accounts in pre-specified meetings

- making sure illiterates are aware of project progress (which could include discussions of accounts and changes in project procedures with CFs)

- checking to see that all members are informed well in advance about project meetings

- public announcements and discussions on training possibilities, choice of trainees and de-briefing of returned trainees

- ensuring that each group member is aware of the responsibilities (and hence extent of accountability) of their group leaders, NGO staff and district government staff, and also

- ensuring that group members are aware of how to initiate complaint procedures if irregularities are detected in the functioning of the leaders of CIGs or VDAs, CFs and NGOs, and even the DPMU staff and other line department officials.

    - Ensuring Effective Capacity Building

Providing training to project stakeholders on group formation, team building, leadership skills, financial management and conflict resolution are all essential to building capacity to implement the project effectively. However, capacity building has to be directed ultimately to achieving the project objective of improving ‘economic opportunities, living standards and social status’ of the poor in the selected areas of the project. This requires more than conducting general trainings for secondary stakeholders in state or district centres.

Essential to the process of building capacity are the following.

- Training CFs to approach government offices to get information on available government schemes and procedures. This is an essential ability that has to be transferred to CIG members to ensure that their ability to access and participate in development processes and economic opportunities.

- Providing CFs and NGO staff with effective conflict resolution techniques and details of successful experiences in the past, which can prepare them for the situations they may face in the future in project villages.

- Providing continuous support to CFs and NGOs, which they will require to tackle new situations and problems on the ground. This could be in the form of either a small Help Desk in the SPMU or the DPMU, to which they can address their queries (e.g., on situations threatening success in micro-enterprise development, or in the participation of women in democratic processes), or a similar but mobile facility which visits each district say once a month and addresses issues face to face with stakeholders, or both.

- Adding a practical demonstration of PRA techniques or conflict resolution techniques to trainees, which can be hosted by different districts in turn, so that trainees can experience ‘learning by doing’, which is more effective than even mock demonstrations in training centres. However, this will require competent training staff.

Since the real test of capacity building is effective demonstration on the ground, the process of building capacity has to monitored and evaluated on whether trainees pass this test – rather than just the number of trainings held, the material distributed, or even the marks scored by trainees at an in-house evaluation at the end of a course.

But making this transition from mere ‘training’ to ‘capacity building’ requires a different approach, and hence, the adoption of a process with additional components.

    - Processes to Achieve Objectives

The ‘spirit’ of the project, as captured in its objectives, approach and provisions, implies a set of processes that are essential to the achievement of project objectives. These go beyond what is currently specified in project guidelines or the implementation plan. Monitoring project processes can thus be seen either in the narrow sense of how well project implementation adheres to the guidelines or in the wider sense of what needs to be done to achieve project objectives. But the success of the project, in the spirit in which it has been formulated, will depend on how well the project managed to achieve its objectives – and not on how well the implementation followed certain guidelines.

  - QPA TO ASSESS PROJECT PROCESSES

2.4.1	Assessing Processes

Project processes, such as capacity building, can be assessed in terms of both activities undertaken (e.g., to build capacity) as well as the outcome of these activities (e.g., skills created). But it is not always clear which is easier to assess, as Table 2.1 illustrates, in terms of the processes assessed during the pilot QPA.

Table 2.1: Assessing Processes: Activities and Impact

| Process | Activities | Outcome |
| --- | --- | --- |
| Awareness generation | Meetings, discussions, camps, leaflets, posters, etc. by CF/NGO | Awareness created of project objectives and benefits |
| Formation of CIG | Announcement by CF/NGO in public forum, identification of poor, discussion among group with CF, open choice of membership, etc. | CIG formed, after informed choice |
| Preparation of sub-project proposal | Discussion organised by CF with a number of experts, short-listing of a few options, further discussions with relevant experts, final choice of activity, clarification of all relevant details of sub-project proposal | Sub-project proposal prepared, and all members aware of details |
| Capacity building | Information given by CF about training opportunities, equal choice of participation to all interested members, special facilitation for women and other under-privileged members | Effective training leading to skills being practised regularly |
| Group Development | CF visits CIG regularly, provides the necessary information, informs group of forthcoming meeting details, teaches CIG how to open bank accounts, and to get information from relevant government offices | Group empowered to access development process |
| Participation in CIG decision making | CF guiding so that all members (and especially women) to have an equal say in CIG decisions | Participatory decision making in CIG |
| Transparency | CF ensures that all members have access to project-related information, regularly during meetings (even without being asked), on demand, and displayed publicly; also ensures illiterates in CIG are aware of CIG functioning (decision-making and finances) | Transparent functioning of CIG with all members aware of activities and finances |

The pilot QPA assessed these processes in terms of activities carried out, except in two cases: awareness generation, where the assessment is based on the outcome (i.e., increased awareness); and capacity building, where assessment is based on both activities and outcome.

2.4.2	Pilot QPA Formats

Keeping in mind the above discussion, the QPA format set out the following questions to capture the extent to which key project processes were being followed in the field. These have been reproduced from the final QPA format used in the pilot and the question numbers correspond to project processes, while sub-questions assess different dimensions (e.g., in Capacity Building).

The options describing each set of ordinal scores reflect the extent to which the process was followed. Thus, the option with a score of 100 reflects an ideal situation, while a score of 0 is an undesirable situation. The option corresponding to a score of 50 is chosen to be a benchmark in that its achievement reflects a satisfactory performance. Scores less than 50 are not satisfactory, while those above 50 are better than satisfactory.

1.	AWARENESS ABOUT THE PROJECT

Q. 1	What do you think the project will do to reduce poverty?

| OPTIONS | SCORES | SCORE |
| --- | --- | --- |
| Give group members 90% subsidy for specific activities | 0 |  |
| Also start saving and loaning activities among members | 25 |  |
| Also give training for members to increase their skills, and help them get bank credit | 50 |  |
| Also give members better access to health, education, drinking water, and other facilities | 75 |  |
| Also, help members get better access to government schemes directly, and through village decision-making | 100 |  |

2.	FORMATION OF GROUPS

Q. 2	How was the CIG formed?

| OPTIONS | SCORES | SCORE |
| --- | --- | --- |
| Individuals were approached by CF and some villagers and asked to join a particular group; no information regarding the project was given in a gram sabha | 0 |  |
| Villagers were informed about the project in a gram sabha, given the option of joining different groups, and formed groups then and there | 25 |  |
| Specific villagers were informed by the CF first, then a gram sabha was held; after which CFs or NGO again discussed available options, and then formed groups | 40 |  |
| Villagers informed about the project in a gram sabha, CFs then went around giving more information and discussing available options and then groups were formed | 50 |  |

3.	PREPARATION OF SUB-PROJECT PROPOSAL

Q. 3 	What was the process of finalising the sub project proposal?

| OPTIONS | SCORES | SCORE |
| --- | --- | --- |
| Decided by CF/NGO or others, but not by group members | 0 |  |
| Decided by CF/NGO or others with a few, but not all, group members | 25 |  |
| Group members discussed a few given options, selected one option, and finalised the proposal with the NGO-provided expert | 50 |  |
| Group members discussed a few given options with NGO-provided experts, jointly selected one option, and finalised the proposal with the expert | 75 |  |
| Group members discussed all possible options with NGO-provided experts, short-listed a few options, jointly selected one option, and finalised the proposal with the expert | 100 |  |

4.	GROUP DEVELOPMENT

Q.4.1	What is the nature of group activities?

| OPTIONS | SCORES | SCORE |
| --- | --- | --- |
| Only saving; no loaning | 0 |  |
| Saving and loaning only for consumption purposes | 25 |  |
| From own savings, loaning without default for at least one productive purpose | 50 |  |
| Also bank loan | 75 |  |
| Also received funds from government development schemes | 100 |  |

Q.4.2	How much has the group developed? (fill in separately for CI and IG groups)

Social infrastructure group

| OPTIONS | SCORES | SCORE |
| --- | --- | --- |
| Has submitted for sub-project proposal | 0 |  |
| Sub-project funds sanctioned | 25 |  |
| Sub-project funds released | 35 |  |
| Also materials purchased | 40 |  |
| Construction work in progress | 45 |  |
| Construction work completed satisfactorily | 50 |  |
| O&M carried out regularly | 75 |  |
| New activity taken up by group | 100 |  |

Income generation group

| OPTIONS | SCORES | SCORE |
| --- | --- | --- |
| Has submitted for sub-project proposal | 0 |  |
| Sub-project funds sanctioned | 25 |  |
| Sub-project funds released | 35 |  |
| Also material purchased | 40 |  |
| Also working capital mobilised (e.g., a bank, or an SHG, etc.) | 45 |  |
| Sub-project activity started | 50 |  |
| Profits made from sub-project activity | 75 |  |
| Expansion of sub-project activity with profits | 100 |  |

Q.4.3	What is the nature of facilitation of group development?

| OPTIONS | SCORES | SCORE |
| --- | --- | --- |
| No facilitation; the CF has not visited the group since the sub project proposal was submitted | 0 |  |
| Some facilitation; CF comes but not regularly and does not provide all the required information | 25 |  |
| Average facilitation; CF comes regularly, gives all required information, and has taught them how to open bank accounts and to maintain account books | 50 |  |
| Good facilitation; In addition, all members know dates of CF’s visits, and know when awareness and training programmes are to be held | 75 |  |
| Excellent facilitation; In addition, CF has taught group how to get information from government offices and to resolve conflicts within the group | 100 |  |

5.	CAPACITY BUILDING

Did members undergo training?		0. 	NO		Go to Question 6

1. 	YES		Continue

What was the focus of training		0.	Improving existing skills

1.	Building new skills

Details of training received

| Subject of Training | Year | No: attended | No: of days attended | Organised by? | Place of training |
| --- | --- | --- | --- | --- | --- |
| 1. |  |  |  |  |  |
| 2. |  |  |  |  |  |
| 3. |  |  |  |  |  |
| 4. |  |  |  |  |  |
| 5. |  |  |  |  |  |

Q.5.1	What was the nature of training opportunities?

| OPTIONS | SCORES | SCORE |
| --- | --- | --- |
| No relevant training was organised for the group | 0 |  |
| Training was organised but group members were not informed | 10 |  |
| Only a few key group members were informed, selected and sent | 25 |  |
| The whole group was informed, and members attended – but training not organised on the basis of the training needs assessment and all who wished to attend (especially women) were not helped to do so | 50 |  |
| Training organised according to the training needs assessment, the entire group was informed and members attended - but all those who wished to attend (especially women & poor) were not helped to do so | 75 |  |
| Training organised according to training needs assessment, the entire group was informed, and all who wished to attend (especially women & poor) were helped to do so | 100 |  |

Q.5.2	Was training effective?

| OPTIONS | SCORES | SCORE |
| --- | --- | --- |
| None of the trainees took the training seriously and did not learn anything | 0 |  |
| Even those who attended seriously could not learn much (e.g., badly organised, bad trainers, etc.) | 25 |  |
| All those who attended seriously learnt the skill sufficiently, are using it effectively | 50 |  |
| All those who attended the training learnt the skill sufficiently; and most are using it effectively | 75 |  |
| All those who attended the training learnt the skill sufficiently; and all are using it effectively | 100 |  |

6.	PARTICIPATION IN DECISION-MAKING

Q.6.1	What is the nature of decision-making within the group?

| OPTIONS | SCORES | SCORE |
| --- | --- | --- |
| Few members take all decisions, others do not speak up even when they have a problem | 0 |  |
| Few members take all decisions, others speak up when they have a problem, but cannot influence decisions | 25 |  |
| Few members take all decisions, others are able to influence decisions that affect them – but no such situation has come up so far | 40 |  |
| Few members take all decisions, but others have been able to influence at least one decision that affected them | 50 |  |
| Decisions are taken by majority rule, but some members are unhappy with decision | 75 |  |
| Decisions are taken by all by consensus (although every member has the right to say No) | 100 |  |

Q.6.2	What is the nature of women’s participation in mixed CIGs?

| OPTIONS | SCORES | SCORE |
| --- | --- | --- |
| Women are group members, but do not attend meetings | 0 |  |
| Women members attend meetings, but do not speak | 25 |  |
| Women members attend and speak and are able to influence decisions that affect them – but no such situation has come up so far | 40 |  |
| Women members speak up on issues concerning them, and have influenced at least one decision | 50 |  |
| Women members speak up even on some group issues and have influenced at least one group decision | 75 |  |
| Women members speak up on all group issues and influence decisions – just like men | 100 |  |

7.	TRANSPARENCY

Q.7	How accessible is project-related information to group members?

| OPTIONS | SCORES | SCORE |
| --- | --- | --- |
| Difficult, CF not available when needed to answer questions | 0 |  |
| Members can get the information from CF, but they do not always know when CF comes | 25 |  |
| Members know when CF comes and get all the information they need from the CF | 50 |  |
| In addition, even without asking, members are given information regularly in meetings | 75 |  |
| In addition, project information is put up on a board, which is accessible to all | 100 |  |

The next section details the results from the QPA Pilot in Dausa and Churu districts.

3. QPA PILOT: ASSESSING DPIP PROCESSESES

## INTRODUCTION

The main results of the QPA Pilot are presented in this section (for details see Annex 2). The results pertain to (1) the Village Assessments, (2) the District Assessments and (3) the District Stakeholder Meeting. The Village Assessment has 3 parts – updated secondary information regarding the village, ordinal scores reflecting the process followed, and details of the sub-project proposed (reflecting the extent to which the community participated in the choice and planning of these sub-projects, as stated in Specific Objective (b)). However, in most cases, it was found that the group was not very aware about the details of the sub-project. For this reason, these results are not discussed further.

  - VILLAGE ASSESSMENTS: MAIN FINDINGS

3.2.1	Secondary Information

#### The following are the main points from the assessments

- There is a large difference between existing secondary information and the current village situation regarding population and household numbers.

- According to villager perception, there are non-poor members in the current BPL list and poor not included in the BPL list.

- Currently, a large proportion (60-90%) of BPL families - and a larger proportion of those considered poor by the villagers - is not in CIGs.

###### Project Processes

The following are satisfactory:

- Formation of CIGs by CFs and NGO after prior information and discussion

- Regularity of CIG meetings

- Democratic decision-making within the group (participation by all members)

- Availability of project information via the CF (transparency)

The following processes can be improved:

- Awareness about (the full range of) project objectives and processes

- Choice of sub-project activity and formulation of proposals

- Group development (as an SHG initially, with adequate documentation to qualify for bank credit).

3.3.	DISTRICT LEVEL FINDINGS

3.3.1	District Stakeholders Meeting

Details of the issues raised and discussed at these stakeholder meetings are in Annexure 2. The major decisions taken at these meetings, both in Churu and in Dausa, are the following.

- Awareness Workshop with Banking Staff – To be organised by the DPMU, for DPIP staff (especially CFs and BCs) to be aware about banking procedures, and for bankers to learn about DPIP and its special characteristics and requirements

- Loans to CIGs on a trial basis – 2 groups each in Dausa and Churu, to be given loans for micro-enterprise activity, relaxing existing rules (e.g., out-of-district purchase in Dausa).

Several other issues were discussed but were referred to the state-level stakeholders’ meeting, since they required action by the SPMU or at state-level.

3.4	STATE LEVEL DISCUSSIONS

The following issues were tabled for discussion during the state-level stakeholders’ meeting, having been raised at the district-level stakeholders’ meetings.

    - Implementation Issues

Revision of Guidelines

- Include project objectives and processes

- Simplify project procedures (e.g., of sub-project appraisal and inclusion of non-BPL poor)

- Clarify roles and responsibilities of DPMU and NGO staff (each individual positions)

- Simplify financial system for DPMU operations

- Clarify phasing of project (e.g., 4 years in worst villages, 3 years in next worst, etc.)

- Revise the strategy of group development (i.e., start CIGs along the SHG route initially)

- Provide for exposure visits and interaction with resource persons for CIGs and CFs prior to sub-project formulation.

- Devolve as much power as possible to the district level (e.g., approval of budget for training).

- Examine the possibility of inducting (unintentional and deserving) defaulters into CIGs.

- Provide for forming associations of CIGs (thematic and geographical).

Revision of NGO contracts

- Separate travel components from salary (e.g., for BCs) and other costs (e.g., village awareness generation programmes and sub-project preparation).

- Make travel allowances realistic (e.g., on the basis of log books for (own) vehicles used)

- Examine possibility of revising CF salary from Rs. 2,000 at present to Rs. 3,000 (as requested by CFs).

- Make salary payments monthly instead of quarterly

- Examine possibility of introducing incentives and penalties on the basis of (qualitative and quantitative) evaluation of field level performance  (e.g., by holding back 10% of payment, to be paid if evaluation is positive, and to be forfeited if evaluation is negative). Also non-monetary incentives (e.g., capacity building exposure visits and workshops for NGO staff).

- Examine possibility of paying 75% of travel claims in advance, and the remaining pending examination of all bills (as done in Government of Rajasthan corporations currently).

- Examine possibility of longer-term contracts for NGOs, to increase their incentive to invest in better performance.

Training

Set down a training strategy which reviews training needs, and – with the training institutions responsible - prepares training plan & calendars for the entire project, including

- Re-orientation of all district and state-level staff (CFs, BCs, DPC, DPM, DPMU staff, and SPMU staff), and LD staff and bankers

- Preparation of training material for district training teams (DTTs).

Coordination of Project Vision across Project Components

To ensure that the Guidelines, communication material, training material, and all project-related information is consistent with the project vision as outlined in the original project documents (Project Appraisal Document and Project Implementation Plan)

Bank finance for working capital

Starting with the basic premise that the World Bank does not permit its loan funds to be used to give working capital subsidies, involve state-level banking institutions.

Provide first charge of banks on CIG assets created in case group fails.

Establish active working relationships with the 5 Regional Rural Banks mandated and funded by NABARD to promote SHG initiatives.

Convergence with other government schemes

CIGs to follow SHG guidelines and procedures (as recognised by banks) to enable them to get bank loans for working capital.

CIGs to also examine the possibility of dovetailing with other government programmes (e.g., SGSY) – and to work towards fulfilling their requirements

DPMU to detail potential schemes for dovetailing with CIGs, and their procedural requirements.

3.4.2	Other Issues Raised

Apart from issues raised from the district level, there were few other suggestions made by the consultant team, which were discussed during the state-level stakeholder meeting.

Process Monitoring

- Participatory audit of qualitative and quantitative issues at various levels, at the end of each year (instead of DA only at the end of 2nd and 4th years)

- Quarterly stakeholder meetings, with sample village visits, to initiate corrective measures at project level.

- Participatory monitoring (with CIGs) of sub-projects.

- Integration of process monitoring into project information base (on the lines suggested by SIMAL).

Information Sharing

- Set up an advisory group of non-government experts to bring in information on promising findings from other projects countrywide, and other innovative initiatives.

- Organise a series of workshops for information and experience sharing with SPMU, with proper reports and follow-up project action, on issues relevant to project performance (e.g., SC order on brick kilns, State Water Policy, Right to Information, etc.)

- Set up district-level ‘ Micro enterprise Clinics’ to review working of sub-projects and address problems faced by CIGs.

Wider Policy Issues

- Compilation of department-wise details of on-going reforms of GoR, and with other NGO and donor-assisted initiatives, & initiate tie-ups.

- Strategy to disseminate findings (within and outside government).

- Improving existing development programmes (starting with RD and moving on to others)

- Linking with DPIP in AP and MP.

    - Decisions taken

While the SPMU undertook to examine all issues raised, it was decided at the meeting itself (1) to hold district awareness workshops with bankers and project staff; and (2) to make a representation to the state-level banking committee (SLBC) to include DPIP-related group loaning on agenda. Training issues were to be looked into during the internal SPMU meeting to be held on 17 November 2001.

4. SCALING UP QPA

## 4.1	INTRODUCTION

There are two major extensions of the utility of the QPA information. First, the information can be stored in a computer database (such as Microsoft ACCESS), and accessed as and when required by project management. Second, this database can be merged with the Performance Tracking System and the Financial Management System, to give project management an integrated look at project implementation in its financial, physical, socio-economic and institutional dimensions.

This section, however, does not go into these possibilities, but is confined to detailing QPA questions to assess a Common Interest Group (CIG) and its members over time. For, as the group matures and develops, not only do its activities change, but so also do expectations about its development. And since these expectations are based on the objectives of the project concerning groups and their members, assessments using the QPA have to be based on these expectations. The section begins by examining the sequence of issues to be assessed over three years of development of a CIG.

4.2	CIG ASSESSMENT ISSUES

While processes of initiating a CIG and its activities as well as the nature of its operation are important during the first year of operation, noting its development over time and the impact of the project on its members are of increasing importance during the second and third year of its development.

4.2.1	Project Processes

The PAD indicates the following key project processes:

- Awareness of project objectives and benefits

- Formation of CIGs

- Preparation of the sub-project proposal

- Group development and facilitation

- Capacity building of CIG members

- Participation in group activities (especially by women and tribals)

- Transparency in CIG operations

- Accountability of CFs and CIG leaders

- Conflict resolution within the CIG

- Implementation of sub-project (including project support to CIGs)

- Support for project withdrawal

The phasing of assessment of project processes is shown in Table 4.1.

Table 4.1: Assessment of Processes in CIG Development

| Processes in CIG Development |  | Year 1 | Year 2 | Year 3 |
| --- | --- | --- | --- | --- |
| 1 | Awareness of project objectives |  |  |  |
| 2 | Formation of CIG |  |  |  |
| 3 | Preparation of sub-project proposal |  |  |  |
| 4 | Group development |  |  |  |
| 5 | Capacity building of CIG members |  |  |  |
| 6 | Participation in group activities (especially by women and tribals) |  |  |  |
| 7 | Transparency in CIG operations |  |  |  |
| 8 | Accountability of CIG leaders |  |  |  |
| 9 | Conflict resolution |  |  |  |
| 10 | Implementation of sub-project |  |  |  |
| 11 | Support for project withdrawal |  |  |  |

4.2.2	Project Impacts

The development objectives of the project are to improve the economic opportunities, living standards and the social status of the poor in selected villages of these districts. Specifically, the project aims to:

- Mobilize and empower the poor and help them to develop strong grassroots organisations that facilitate access to and participation in democratic and development processes.

- Support small-scale sub-projects that are priorities chosen, planned and implemented by the poor.

- Expand the involvement of the poor in economic activities by improving their capacities, skills, access to social and economic infrastructure and services, and employment opportunities

- Improve the abilities of non-government, government and elected government (PR) institutions to hear, reach and serve poor clients, i.e., to function in a more inclusive and participatory manner.

Keeping these in mind, the major project impacts expected at the end of the project period can be listed as follows.

- Improved living standards and social status: While improved living standards basically comprise increased employment, income, assets and reduced indebtedness, improved social status will include increased participation in village meetings and activities and reduced discrimination (especially against women).

- Development of strong grassroots organisations: Transparency, accountability and conflict resolution are characteristics of a strong grassroots organisation.

- Benefits from small-scale sub-projects: CIG members are to choose, plan and implement these sub-projects, but in the final analysis they have to provide sustainable income to participating members.

- Improved capacities and skills: Both, the processes to build capacity and skill, and the impact of these activities (i.e., effectiveness of capacity building), are relevant, but are assessed under processes.

- Improved access to social and economic infrastructure and services: Increased reliance to bank credit and, correspondingly, reduced dependence on moneylenders is an important aspect of improved access to economic infrastructure and services. Increased access to social infrastructure includes water and sanitation facilities, as well as education and health.

- Improved access to employment opportunities: This is a strong case where assessing only the actual increase in employment may not reflect the efforts put in by project staff to improve access to employment opportunities.

- Access and participation in democratic processes: While participation in village meetings and activities is relevant, so also is participation in CIG activities (covered under project processes).

- Access and participation in development processes: This can be assessed in terms of awareness of available government programmes, as well as assistance and support from government agencies, in addition to actual beneficiaries of various government programmes.

- Improved abilities of non-government, government and elected government institutions to hear, reach and serve the poor: Separate assessment of NGO, government and Panchayati Raj institutions are required, in terms of (1) efforts by the project to function in a ‘more inclusive and participatory manner’, (2) the actual changes effected in their manner of functioning, and (3) the impact of these changes on the poor.

These impacts can only be assessed in the second and third years (see Table 4.2).

Table 4.2: Assessment of Impacts of CIG Development

| Impacts of CIG Development |  | Year 1 | Year 2 | Year 3 |
| --- | --- | --- | --- | --- |
|  | Improved living standards and social status |  |  |  |
| 1 | Economic impact (more income, assets and reduced indebtedness) |  |  |  |
| 2 | Agricultural production and productivity |  |  |  |
| 3 | Social status of members |  |  |  |
|  | Benefits from small-scale sub-projects |  |  |  |
| 4 | Economic impact of sub-projects |  |  |  |
|  | Development of strong grassroots organisations |  |  |  |
| 5 | Support linkages with other organisations |  |  |  |
|  | Improved access to social and economic infrastructure and services |  |  |  |
| 6 | Health care |  |  |  |
| 7 | Education |  |  |  |
| 7 | Adequate safe drinking water |  |  |  |
| 8 | Adequate sanitation facilities |  |  |  |
|  | Improved access to employment opportunities |  |  |  |
|  | Access and participation in democratic processes |  |  |  |
| 9 | Participation in general village decision-making |  |  |  |
| 10 | Member satisfaction with CIG and sub-project performance |  |  |  |
|  | Access and participation in development processes |  |  |  |
| 11 | Awareness about government programmes and schemes |  |  |  |
| 12 | Participation in government programmes and schemes |  |  |  |
|  | Improved abilities of non-government, government and elected government institutions to hear, reach and serve the poor |  |  |  |
| 13 | Changes in the operation of these institutions to facilitate the poor |  |  |  |

4.3	QPA Formats for Phased Assessments

Since the QPA formats for assessment of CIG development in Year 1 have been detailed earlier (see section 2.4.2), this sub-section lists QPA questions for use in years 2 and 3, based on the discussion above. However, a list of processes to be assessed in Year 1 is given in Table 4.3.

Table 4.3: Project Processes to be Assessed in Year 1

| 1.1 | Awareness of project objectives |
| --- | --- |
| 1.2 | Formation of CIG |
| 1.3 | Preparation of sub-project proposal |
| 1.4 | Group development |
| 1.5 | Capacity building of CIG members |
| 1.6 | Participation in group activities (especially by women and tribals) |
| 1.7 | Transparency in CIG operations |

Note that while the formats to assess the above issues have been piloted in the field, the formats for assessments in years 2 and 3 have to be field-tested. They are, thus, provisional and subject to revision.

4.3.1	QPA Formats for Years 2

Table 4.4  shows the processes and impacts to be assessed in Year 2 of CIG development. Italics denote additional processes and impacts to be assessed in that year, compared to the previous year.

Table 4.4: Processes and Impacts to be Assessed in Year 2

| Project Processes |  |
| --- | --- |
| 2.1 | Group development |
| 2.2 | Capacity building of CIG members |
| 2.3 | Participation in group activities (especially by women and tribals) |
| 2.4 | Transparency in CIG operations |
| 2.5 | Accountability of CIG leaders |
| 2.6 | Conflict resolution |
| 2.7 | Implementation of sub-project |
| Project Impacts |  |
| 2.8 | Support linkages with other organisations |
| 2.9 | Health care |
| 2.10 | Education |
| 2.11 | Adequate safe drinking water |
| 2.12 | Adequate sanitation facilities |
| 2.13 | Participation in general village decision-making |
| 2.14 | Member satisfaction with CIG and sub-project performance |
| 2.15 | Awareness about government programmes and schemes |

The QPA questions and scored options for the  additional issues in Year 2 are given below.

Issue 2.5 	Accountability of CIG Leaders

2.5	Do CIG Leaders take decisions only after consulting CIG members?

| OPTIONS | SCORES | SCORE |
| --- | --- | --- |
| No formal or informal arrangements to check CIG leader; can do as they please | 0 |  |
| Rules exist but are not always followed; CIG leader has taken some decisions on their own which the group is not happy about | 25 |  |
| Rules exist but are not always followed; CIG leader has taken some decisions on their own BUT the group is happy with these decisions | 40 |  |
| No rule, but CIG leader has never taken decisions without consulting group members | 50 |  |
| Informal rules exist to ensure CIG leader consults members, and these are always followed; CIG leader has never taken decisions without consulting group members | 75 |  |
| Formal rules exist and are always followed | 100 |  |

Issue 2.6	Conflict Resolution

2.6	Are there conflicts within the CIG?

| OPTIONS | SCORES | SCORE |
| --- | --- | --- |
| CIG not functioning due to conflicts between members | 0 |  |
| Formal procedures exist to resolve conflict, but at least one conflict has not been resolved | 25 |  |
| No formal procedures, but CIG has resolved all conflicts successfully till now | 50 |  |
| Formal procedures exist to resolve conflict, and all conflicts successfully resolved till now using these procedures – but not using these procedures | 75 |  |
| Formal procedures exist to resolve conflict, and all conflicts successfully resolved till now using these procedures | 100 |  |

Issue 2.7	Implementation of Sub-Project

2.7	Is the sub-project generating benefits?

| OPTIONS | SCORES | SCORE |
| --- | --- | --- |
| Sub-project has not been implemented so far | 0 |  |
| Sub-project implemented; but no benefits so far | 25 |  |
| Sub-project implemented; some benefits so far, but not as much as expected | 50 |  |
| Sub-project implemented; benefits as expected | 75 |  |
| Sub-project implemented; more benefits than expected | 100 |  |

Issue 2.8	Support linkages with other organisations

2.8	Does the group receive support from panchayats, banks and government offices?

| OPTIONS | SCORES | SCORE |
| --- | --- | --- |
| No efforts to forge linkages with Panchayat, banks and government offices; no assistance received from these organisations. | 0 |  |
| Some efforts made to forge linkages; but no effective assistance received so far | 25 |  |
| Efforts made to forge linkages; at least one example of support received from Panchayat, banks and government offices | 50 |  |
| Several examples of support received from Panchayat, banks and government offices, but no efforts to maintain linkages | 75 |  |
| Several examples of support received from Panchayat, banks and government offices; active efforts to maintain linkages | 100 |  |

The assessment of whether the group has developed a strong grassroots organisation has to be taken in conjunction with the responses to the questions on transparency (1.7), accountability (2.5) and conflict resolution (2.6).

Issue 2.9	Health Care

2.9	Do group members know where to get medical help?

| OPTIONS | SCORES | SCORE |
| --- | --- | --- |
| No change from situation before DPIP | 0 |  |
| Few more group members now know how to get medical help when required | 25 |  |
| Every member of the group now knows how to get medical help when required, but no one member has practical experience of doing so. | 50 |  |
| Every member of the group now knows how to get medical help when required, and one member has practical experience of doing so. | 75 |  |
| Every member of the group now knows how to get medical help when required, and more than one member has practical experience of doing so. | 100 |  |

Issue 2.10	Education

2.10	Are the children of group members benefiting from school education?

| OPTIONS | SCORES | SCORE |
| --- | --- | --- |
| No change from situation before DPIP | 0 |  |
| Some more school-age children of group members are attending school, after DPIP | 25 |  |
| All school-age children of group members are attending school, after DPIP | 50 |  |
| In addition, most have passed last year’s examinations | 75 |  |
| In addition, all have passed last year’s examinations | 100 |  |

Issue 2.11	Access to Adequate and Safe Water

2.11	Do group members have better access to adequate and safe water?

| OPTIONS | SCORES | SCORE |
| --- | --- | --- |
| No change in access to adequate and safe water after project | 0 |  |
| Improved access, but not due to DPIP | 25 |  |
| At least one member has access to more water with less time due to DPIP, but not all | 50 |  |
| Most members have access to more water with less time due to DPIP, but not all | 75 |  |
| All members have access to more water with less time due to DPIP | 100 |  |

Issue 2.12	Access to Adequate Sanitation Facilities

2.12	Do group members have better access to adequate sanitation facilities?

| OPTIONS | SCORES | SCORE |
| --- | --- | --- |
| No change in access to adequate sanitation facilities after DPIP | 0 |  |
| Improved access, but not due to DPIP | 25 |  |
| At least one member has a working toilet due to DPIP, but not all | 50 |  |
| Most members have access to working toilets due to DPIP, but not all | 75 |  |
| All members have access to working toilets due to DPIP | 100 |  |

Issue 2.13	Participation in general village decision-making

2.13	Do group members participate in village decision-making?

| OPTIONS | SCORES | SCORE |
| --- | --- | --- |
| No change in group members’ participation in village activities after DPIP | 0 |  |
| Group members now participate more in village activities, but have not changed even one decision to their benefit or that hurt their interests | 25 |  |
| Group members now participate more in village activities and have changed one decision to their benefit or prevented one decision that hurt their interests | 50 |  |
| Group members now participate more in village activities and have changed few decisions to their benefit or that hurt their interests | 75 |  |
| Group members now participate more in village activities and have changed all decisions to their benefit or that hurt their interests | 100 |  |

Issue 2.14	Member satisfaction with CIG and sub-project performance

2.14	Are group members happy with CIG performance?

| OPTIONS | SCORES | SCORE |
| --- | --- | --- |
| All members are dissatisfied with one or more aspects of CIG performance | 0 |  |
| Some members are dissatisfied with one or more aspects of CIG performance | 25 |  |
| No member is dissatisfied with CIG performance, but feel improvements are necessary | 50 |  |
| No member is dissatisfied with CIG performance, and feel only few improvements are possible | 75 |  |
| No member is dissatisfied with CIG performance, and all feel that no improvements are necessary or possible | 100 |  |

Issue 2.15	Awareness about government programmes and schemes

2.15	Do group members know about available government programmes?

| OPTIONS | SCORES | SCORE |
| --- | --- | --- |
| No change from situation before DPIP | 0 |  |
| Few more group members now know about available government programmes and schemes, and how to access them | 25 |  |
| Every member of the group now knows about available government programmes and schemes, and how to access them, but no member has practical experience of doing so. | 50 |  |
| Every member of the group now knows about available government programmes and schemes, and how to access them, and one member has practical experience of doing so. | 75 |  |
| Every member of the group now knows about all available government programmes and schemes, and how to access them, and more than one member has practical experience of doing so. | 100 |  |

4.3.2	QPA Formats for Year 3

Table 4.5 specifies the processes and impacts to be assessed in Year 3 of CIG development. Once again, italics denote additional issues to be assessed compared to the previous year.

Table 4.5: Processes and Impacts to be Assessed in Year 3

| Project Processes |  |
| --- | --- |
| 3.1 | Group development |
| 3.2 | Capacity building of CIG members |
| 3.3 | Participation in group activities (especially by women and tribals) |
| 3.4 | Transparency in CIG operations |
| 3.5 | Accountability of CFs and CIG leaders |
| 3.6 | Conflict resolution |
| 3.7 | Implementation of sub-project |
| 3.8 | Support for project withdrawal |
| Project Impacts |  |
| 3.9 | Health care |
| 3.10 | Attendance and performance in schools |
| 3.11 | Adequate safe drinking water |
| 3.12 | Adequate sanitation facilities |
| 3.13 | Participation in general village decision-making |
| 3.14 | Member satisfaction with CIG and sub-project performance |
| 3.15 | Awareness about government programmes and schemes |
| 3.16 | Economic impact (more income, assets and reduced indebtedness) |
| 3.17 | Agricultural production and productivity |
| 3.18 | Social status of members |
| 3.19 | Participation in government programmes and schemes |
| 3.20 | Changes in the operation of NGOs, GOs and PRIs to facilitate access by the poor |

The additional QPA formats for assessing project performance in Year 3 are given below.

Issue 3.8	Support for project withdrawal

Q.3.8	Have any special arrangements been made for the CIG after the project ends?

| OPTIONS | SCORES | SCORE |
| --- | --- | --- |
| No provisions or arrangements made for CIG after project ends | 0 |  |
| CIG has been informed about project ending, but nothing further | 25 |  |
| CIG has been informed about date, CF/NGO has instructed CIG on how work should carry on, and group members know which government offices to go to for further help | 50 |  |
| In addition, CF/NGO has arranged for group to meet concerned government officials to make linkages for future support, but members have not yet gone for any assistance | 75 |  |
| In addition, CF/NGO has arranged for group to meet concerned government officials to make linkages for future support, and at least one member has successfully got assistance. | 100 |  |

Issue 3.16	Economic impact (more income, assets and reduced indebtedness)

Q.3.16.1	Has the income of group members increased due to DPIP?

| OPTIONS | SCORES | SCORE |
| --- | --- | --- |
| No change from before project, for all group members | 0 |  |
| Some change for few group members | 25 |  |
| Some change for all group members | 50 |  |
| Some change for all; but substantial change for some | 75 |  |
| Substantial change for all members | 100 |  |

Q.3.16.2	Have group members purchased new assets due to DPIP?

| OPTIONS | SCORES | SCORE |
| --- | --- | --- |
| No change from before project, for all group members | 0 |  |
| Some change for few group members | 25 |  |
| Some change for all group members | 50 |  |
| Some change for all; but substantial change for some | 75 |  |
| Substantial change for all members | 100 |  |

Q.3.16.3	Has the indebtedness of group members reduced due to DPIP?

| OPTIONS | SCORES | SCORE |
| --- | --- | --- |
| No change from before project, for all group members | 0 |  |
| Some change for few group members | 25 |  |
| Some change for all group members | 50 |  |
| Some change for all; but substantial change for some | 75 |  |
| Substantial change for all members | 100 |  |

Issue 3.17	Agricultural production and productivity

Note that these assessments use the indices of change method.

3.17.1	Changes in agricultural production

|  | Before DPIP = 100 | After DPIP |
| --- | --- | --- |
| Total cultivated area in village |  |  |
| Total irrigated area in village |  |  |
| Total production in the village |  |  |

3.17.1	Changes in agricultural productivity

| Major crops | Before DPIP = 100 | After DPIP |
| --- | --- | --- |
| Irrigated |  |  |
| 1. |  |  |
| 2. |  |  |
| 3. |  |  |
| Rained |  |  |
| 1. |  |  |
| 2. |  |  |
| 3. |  |  |

Issue 3.18	Social Status of Members

Q.3.18	Do members feel their social status within the village has improved after DPIP?

| OPTIONS | SCORES | SCORE |
| --- | --- | --- |
| No change from before project, for all group members | 0 |  |
| Some change for few group members | 25 |  |
| Some change for all group members | 50 |  |
| Some change for all; but substantial change for some | 75 |  |
| Substantial change for all members | 100 |  |

Issue 3.19	Participation in government programmes and schemes

Q.3.19		Do more members participate in government programmes after DPIP?

| OPTIONS | SCORES | SCORE |
| --- | --- | --- |
| No change from situation before DPIP | 0 |  |
| Few have participated in government programmes after DPIP, but no benefits yet | 25 |  |
| Some members have received benefits from government programmes after DPIP | 50 |  |
| Most members have received benefits from government programmes after DPIP | 75 |  |
| All members have received benefits from government programmes after DPIP | 100 |  |

Issue 3.20	Changes in the operation of NGOs, GOs and PRIs to facilitate access by the poor

Q.3.20.1	Is the NGO more accessible now?

| OPTIONS | SCORES | SCORE |
| --- | --- | --- |
| No change from situation before DPIP | 0 |  |
| Slight improvement after DPIP | 25 |  |
| Some improvement after DPIP | 50 |  |
| Major improvement after DPIP | 75 |  |
| Substantial improvement after DPIP | 100 |  |

Q.3.20.2	Are Line Department offices more accessible now?

| OPTIONS | SCORES | SCORE |
| --- | --- | --- |
| No change from situation before DPIP | 0 |  |
| Slight improvement after DPIP | 25 |  |
| Some improvement after DPIP | 50 |  |
| Major improvement after DPIP | 75 |  |
| Substantial improvement after DPIP | 100 |  |

Q.3.20.2	Are local government offices (panchayat samiti, BDO, etc.) more accessible now?

| OPTIONS | SCORES | SCORE |
| --- | --- | --- |
| No change from situation before DPIP | 0 |  |
| Slight improvement after DPIP | 25 |  |
| Some improvement after DPIP | 50 |  |
| Major improvement after DPIP | 75 |  |
| Substantial improvement after DPIP | 100 |  |

4.4	SAMPLING AND LOGISTICS

4.4.1	Sampling

There are several options to assess DPIP villages in 7 districts using the QPA methodology, depending on the resources and time available. At the minimum, it would be useful to include three categories of villages to be sampled.

  - A fixed proportion of new villages to be sampled each year

  - Some villages where CIGs have reported problems and some showing good results

  - Some villages that are repeated from the previous year’s sample

Table 4.6 gives the number of villages to be covered in 7 districts during the project period (reproduced from the PIP, February 2000).

Table 4.6: Phasing of Project Areas

| Year | Period | Districts |  |  |  |  |  |  | Yearly Totals |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Rajsamand | Baran | Churu | Dausa | Dholpur | Jhalawar | Tonk |  |
| 1 | 2000-2001 | 69 | 62 | 32 | 99 | 59 | 108 | 47 | 476 |
| 2 | 2001-2002 | 143 | 155 | 74 | 232 | 98 | 216 | 119 | 1037 |
| 3 | 2002-2003 | 190 | 301 | 244 | 183 | 91 | 370 | 291 | 1670 |
| 4 | 2003-2004 | 221 | 307 | 260 | 150 | 156 | 564 | 439 | 2097 |
| 5 | 2004-2005 | 266 | 245 | 316 | 345 | 147 | 190 | 123 | 1632 |
| District Totals |  | 889 | 1070 | 926 | 1009 | 551 | 1448 | 1019 | 6912 |

It is assumed that every year fresh villages are to be adopted, and that the project aims to cover a total of 6,912 distinct villages over its span of 5 years. Further assuming that the QPA is to be done in 10% of project villages, the number of villages to be covered in each district during the project period is given in Table 4.7.

Table 4.7: Ten Percent Sample of Project Villages

| Year | Period | Districts |  |  |  |  |  |  | Annual Totals | Cumulative Totals |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Rajsamand | Baran | Churu | Dausa | Dholpur | Jhalawar | Tonk |  |  |
| 1 | 2000-2001 | 7 | 6 | 3 | 10 | 6 | 11 | 5 | 48 | 48 |
| 2 | 2001-2002 | 14 | 16 | 7 | 23 | 10 | 22 | 12 | 104 | 151 |
| 3 | 2002-2003 | 19 | 30 | 24 | 18 | 9 | 37 | 29 | 167 | 318 |
| 4 | 2003-2004 | 22 | 31 | 26 | 15 | 16 | 56 | 44 | 210 | 528 |
| 5 | 2004-2005 | 27 | 25 | 32 | 35 | 15 | 19 | 12 | 163 | 691 |
| District Totals |  | 89 | 107 | 93 | 101 | 55 | 145 | 102 | 691 |  |

If the assessment is to start from project year 3 (i.e., 2002-2003), a cumulative total of 3,180 villages should have been covered by the end of this year, provided implementation is proceeding according to plan. Given a fixed coverage of 10% of new project villages, this will mean that 318 new villages will have to be assessed in 2002-2003. In project year 4 (2003-2004), there will be 210 new villages to be covered. If repeated sampling is restricted to 40% of the previous year’s villages, 127 villages will have to be covered. In addition, if 10% of the previous year’s villages are selected  for special case coverage (bad cases or good cases), the total number of villages to be covered in 2003-2004 will be 369. In project year 5 (2004-2005), there will be 163 new villages, 211 repeats (40% of the total assessed in project years 3 an 4), and 53 fresh cases (10% of the total of project years 3 and 4), 427 in all. Similarly for project year 6 (2005-2006), which is the only year to assess repeat villages from 2004-2005, there will be 314 villages to be covered. A total of 1429 villages will be assessed (see Table 4.8)

Table 4.8: Suggested sampling scheme for possible QPA assessment

| Year | Period | 10% of annual Coverage | New | Repeats | Special Cases | Total Sample | Cumulative Total |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 2000-2001 | 48 | 0 | 0 | 0 | 0 | 0 |
| 2 | 2001-2002 | 104 | 0 | 0 | 0 | 0 | 0 |
| 3 | 2002-2003 | 167 | 318 | 0 | 0 | 318 | 318 |
| 4 | 2003-2004 | 210 | 210 | 127 | 32 | 369 | 687 |
| 5 | 2004-2005 | 163 | 163 | 211 | 53 | 427 | 1114 |
| 6 | 2005-2006 | 0 | 0 | 276 | 37 | 314 | 1428 |

Assuming that one assessment team (of 4 persons) covers 3 villages per week (as per the findings of the pilot QPA), then the time taken to assess the total number of villages calculated for each of the project years 3, 4, 5 and 6 are given in Table 4.9

Table 4.9: Estimated Time for Annual Assessments

| No: of Teams | No: of villages per week* | Year 3 |  | Year 4 |  | Year 5 |  | Year 6 |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Villages | Weeks | Villages | Weeks | Villages | Weeks | Villages | Weeks |
| 4 | 12 | 318 | 27 | 369 | 31 | 427 | 36 | 314 | 26 |
| 6 | 18 | 318 | 18 | 369 | 20 | 427 | 24 | 314 | 17 |
| 8 | 24 | 318 | 13 | 369 | 15 | 427 | 18 | 314 | 13 |
| 10 | 30 | 318 | 11 | 369 | 12 | 427 | 14 | 314 | 10 |
| 12 | 36 | 318 | 9 | 369 | 10 | 427 | 12 | 314 | 9 |
| 14 | 42 | 318 | 8 | 369 | 9 | 427 | 10 | 314 | 7 |
| 16 | 48 | 318 | 7 | 369 | 8 | 427 | 9 | 314 | 7 |
| 18 | 54 | 318 | 6 | 369 | 7 | 427 | 8 | 314 | 6 |
| 20 | 60 | 318 | 5 | 369 | 6 | 427 | 7 | 314 | 5 |

* Assuming that one assessment team can cover 3 villages per week

Thus, the assessment can take 10-14 weeks if 10 assessment teams are used.

If CFs are used for the assessment, and transport and lodging expenses are borne by the DPMU or DPC, the cost of conducting assessments will be restricted to the daily allowance to be paid for the assessment team, and supervision and monitoring costs. Taking the daily allowance to be Rs. 150 on average for the four assessment years, works out to about Rs. 600 per team or per village. Adding Rs. 400 per village for stationery, incidentals, fuel costs and contingencies, gives a figure of Rs. 1000 per village. For 1,428 villages over 4 years, this is Rs. 14,28,000, say Rs. 14.50 lakhs (or Rs. 3.60 lakhs per year).

REFERENCES

Gross, Bruce, Christine van Wijk and Nilanjana Mukherjee, (2001). Linking Sustainability with Demand, Gender and Poverty: A study in Community-Managed Water Supply Projects in 15 Countries, New Delhi, World Bank Water and Sanitation Program and IRC International Water and Sanitation Centre.

James, A. J., (2001a). ‘Enhancing the “Assessment” in Participatory Assessments’, in IFAD, ANGOC and IIRR, Enhancing Ownership and Sustainability: A resource book on participation, International Fund for Agricultural Development (IFAD), Asian NGO Coalition for Agrarian Reform and Rural Development (ANGOC) and International Institute for Rural Reconstruction (IIRR), Part 3.

James, A. J., V. K. Pangtey, Pratibha Singh and Keith Virgo, (2001b). Bringing People’s Perceptions to Project Management Desktops: A Quantified Participatory Assessment of the Doon Valley Watershed Project in North India’, paper presented at the National Workshop on Watershed Management Strategies in Uttaranchal State, Dehradun, 20 – 22 July 2001.

James, A. J., (2000a). MPA: A Methodology for Participatory Assessments’, Waterlines, October.

James, A. J., (2000b). ‘Socio-economic and environmental impact of the Doon Valley Integrated Watershed Management Project, Dehradun’ Project report submitted to WS Atkins International, UK.

James, A. J., and M. Snehalata, (2002a). ‘Quantified Participatory Assessments for the Water Resources Audit of APRLP: Dhone Mandal, Kurnool District’, a report submitted to the Department for International Development (DFID), New Delhi, March 2002.

James, A. J., and M. Snehalata, (2002b). ‘Quantified Participatory Assessments for the Water Resources Audit of APRLP: Kalyandurg Mandal, Anantapur District’, a report submitted to the Department for International Development (DFID), New Delhi, March 2002.

James, A. J., and Rakesh Kaushik, (2000),  System of Integrated Monitoring, Assessment and Learning (SIMAL) for the District Poverty Initiatives Project (DPIP), Rajasthan’, Report submitted to the World Bank, New Delhi Office, November.

PAD (2000), Project Appraisal Document … for a Rajasthan District Poverty Initiatives Project, Report No: 20203–IN, World Bank, South Asia Regional Office, 31 March 2000.

PIP (2000), Rajasthan District Poverty Initiatives Project: Implementation Plan, February 2000.

ANNEX 1

Pilot QPA Formats

QUANTIFIED PARTICIPATORY ASSESSMENTS (QPA)

##### VILLAGE & CIG ASSESSMENT

# DISTRICT POVERTY INITIATIVES PROJECT (DPIP), RAJASTHAN

# Write in Block Letters

| NAME OF BLOCK |  |
| --- | --- |
| NAME OF VILLAGE |  |
| DATE OF ASSESSMENT |  |

| # NAME OF ASSESSMENT TEAM LEADER | # MALE/FEMALE |
| --- | --- |

| NAMES OF ASSESSMENT TEAM MEMBERS |  | MALE/FEMALE |
| --- | --- | --- |
| 1 |  | MALE/FEMALE |
| 2 |  | MALE/FEMALE |
| 3 |  | MALE/FEMALE |
| 4 |  | MALE/FEMALE |
| 5 |  | MALE/FEMALE |
| 6 |  | MALE/FEMALE |

| START TIME |  |
| --- | --- |

A. COMMUNITY LEADERS MEETING: GENERAL VILLAGE INFORMATION

# Demographic Information

|  | No: | Comments |
| --- | --- | --- |
| POPULATION |  |  |
| NO: OF HOUSEHOLDS |  |  |
| NO: OF SC |  |  |
| NO: OF ST |  |  |
| NO: OF WOMEN HEADED HOUSEHOLDS |  |  |
| NO: OF PERSONS WITH DISABILITIES |  |  |
| Lame |  |  |
| Blind, deaf, mute, etc. |  |  |
| Mentally handicapped |  |  |
| TOTAL |  |  |
| NO: OF TRADITIONAL ARTISANS |  |  |
| NO: OF BPL FAMILIES |  |  |
| NO: OF POOR NOT IN BPL LIST |  |  |
| FAMILIES MIGRATING EACH YEAR |  |  |

# Farmers and Landless

| NO: OF MARGINAL FARMERS (< 1 HA) |  |  |
| --- | --- | --- |
| NO: OF SMALL FARMERS (1 – 2 HA) |  |  |
| NO: OF OTHER FARMERS (> 2 HA) |  |  |
| NO: OF LANDLESS |  |  |

# Wage rates & Interest rates

| LOCAL DAILY WAGE RATE (MALE) |  |  |
| --- | --- | --- |
| LOCAL DAILY WAGE RATE (FEMALE) |  |  |
| LOCAL INTEREST RATES (average) |  |  |
| LOCAL BANK INTEREST RATE |  |  |

Access To Social & Economic Infrastructure

| Item | No: | Distance From Village | #### Details |
| --- | --- | --- | --- |
| PUCCA ROAD |  |  |  |
| POST OFFICE |  |  |  |
| PUBLIC TELEPHONES |  |  |  |
| BALWADI |  |  |  |
| PRIMARY SCHOOL (government) |  |  |  |
| PRIMARY SCHOOL (private) |  |  |  |
| SECONDARY SCHOOL (government) |  |  |  |
| SECONDARY SCHOOL (private) |  |  |  |
| HEALTH CENTRE |  |  |  |
| HOSPITAL |  |  |  |
| VETERINARY CENTRE |  |  |  |
| DAIRY COOPERATIVE SOCIETY |  |  |  |
| OILSEEDS COOPERATIVE SOCIETY |  |  |  |
| MANDI |  |  |  |
| MARKET YARD |  |  |  |
| TRAINING CENTRES |  |  |  |
| MAHILA MANDAL |  |  |  |
| FAIR PRICE SHOP |  |  |  |
| DIESEL/PETROL OUTLET |  |  |  |
| ELECTRICITY |  |  |  |
| INDUSTRIAL UNITS |  |  |  |
| MINES |  |  |  |

# Land Details

|  | Total |  |  |  |
| --- | --- | --- | --- | --- |
| GEOGRAPHICAL AREA |  |  |  |  |
| FOREST LAND (Junglaat) |  |  |  |  |
| PASTURE LAND (Gauchar) |  |  |  |  |
|  |  | Kharif | Rabi | Zaid |
| CULTIVATED AREA |  |  |  |  |
| IRRIGATED AREA |  |  |  |  |

# Drinking Water

|  | #### Total | Functional |
| --- | --- | --- |
| OPEN WELLS |  |  |
| DUG-CUM-BORE WELLS |  |  |
| HANDPUMPS ON BOREWELLS |  |  |
| HOUSE TAP CONNECTIONS |  |  |
| IRRIGATION BOREWELLS |  |  |

# Water Quality

| NO: OF DRINKING WATER BOREWELLS AFFECTED BY FLOURIDE |  |
| --- | --- |
| NO: OF IRRIGATION BOREWELLS AFFECTED BY FLOURIDE |  |
| NO: OF DRINKING WATER BOREWELLS AFFECTED BY SALINITY |  |
| NO: OF IRRIGATION BOREWELLS AFFECTED BY SALINITY |  |

# Details of poor who are not in groups?

| Primary Occupation | No: Of Households In The Village |  |  |  |
| --- | --- | --- | --- | --- |
|  | Total | Considered Poor | Considered Not Poor | Considered Poor and in Groups |
| Landless labour |  |  |  |  |
| Small and Marginal Farmers |  |  |  |  |
| Other farmers |  |  |  |  |
| Disabled |  |  |  |  |
| Traditional artisans |  |  |  |  |
| Traders & shopkeepers |  |  |  |  |
| Priests |  |  |  |  |
| Others (SPECIFY) |  |  |  |  |

Comments and observations

Number & type of CIGs

|  | Name of CIG | Members | Number of Members |  |
| --- | --- | --- | --- | --- |
| Income generating activities |  |  | MALE | FEMALE |
| 1 |  | MEN/WOMEN/MIXED |  |  |
| 2 |  | MEN/WOMEN/MIXED |  |  |
| 3 |  | MEN/WOMEN/MIXED |  |  |
| 4 |  | MEN/WOMEN/MIXED |  |  |
| 5 |  | MEN/WOMEN/MIXED |  |  |
| Social Infrastructure |  |  |  |  |
| 1 |  | MEN/WOMEN/MIXED |  |  |
| 2 |  | MEN/WOMEN/MIXED |  |  |
| 3 |  | MEN/WOMEN/MIXED |  |  |
| 4 |  | MEN/WOMEN/MIXED |  |  |
| 5 |  | MEN/WOMEN/MIXED |  |  |
| Land based activities |  |  |  |  |
| 1 |  | MEN/WOMEN/MIXED |  |  |
| 2 |  | MEN/WOMEN/MIXED |  |  |
| 3 |  | MEN/WOMEN/MIXED |  |  |
| 4 |  | MEN/WOMEN/MIXED |  |  |
| 5 |  | MEN/WOMEN/MIXED |  |  |

Is there a VDA in the village?						1. YES		0. NO

Is there a watershed programme in the village?				1. YES		0. NO

If so, when did it start? _____________

Is there any unutilised or incomplete infrastructure available in the village? 	1. YES     	0. NO

If YES, give details: _______________________________________________________________

| ENDING TIME |  | TOTAL TIME |  |
| --- | --- | --- | --- |

##### B.  CIG MEETING

##### Members of the CIG  (Put a * against the name of the CIG Leader)

|  | NAME OF CIG MEMBER | SEX (M/F) | PRESENT? (Yes/No) |
| --- | --- | --- | --- |
| 1 |  |  |  |
| 2 |  |  |  |
| 3 |  |  |  |
| 4 |  |  |  |
| 5 |  |  |  |
| 6 |  |  |  |
| 7 |  |  |  |
| 8 |  |  |  |
| 9 |  |  |  |
| 10 |  |  |  |
| 11 |  |  |  |
| 12 |  |  |  |
| 13 |  |  |  |
| 14 |  |  |  |
| 15 |  |  |  |

| STARTING TIME |  |
| --- | --- |

- AWARENESS ABOUT THE PROJECT

What do you think the project will do to reduce poverty?

| OPTIONS | SCORES | SCORE |
| --- | --- | --- |
| Give group members 90% subsidy for specific activities | 0 |  |
| Also start saving and loaning activities among members | 25 |  |
| Also give training for members to increase their skills, and help them get bank credit | 50 |  |
| Also give members better access to health, education, drinking water, and other facilities | 75 |  |
| Also, help members get better access to government schemes directly, and through village decision-making | 100 |  |

Reasons for score

- FORMATION OF GROUPS

How was the CIG formed?

| OPTIONS | SCORES | SCORE |
| --- | --- | --- |
| Individuals were approached by CF and some villagers and asked to join a particular group; no information regarding the project was given in a gram sabha | 0 |  |
| Villagers were informed about the project in a gram sabha, given the option of joining different groups, and formed groups then and there | 25 |  |
| Specific villagers were informed by the CF first, then a gram sabha was held; after which CFs or NGO again discussed available options, and then formed groups | 40 |  |
| Villagers informed about the project in a gram sabha, CFs then went around giving more information and discussing available options and then groups were formed | 50 |  |

Reasons for score

- PREPARATION OF SUB-PROJECT PROPOSAL

What was the process of finalising the sub project proposal?

| OPTIONS | SCORES | SCORE |
| --- | --- | --- |
| Decided by CF/NGO or others, but not by group members | 0 |  |
| Decided by CF/NGO or others with a few, but not all, group members | 25 |  |
| Group members discussed a few given options, selected one option, and finalised the proposal with the NGO-provided expert | 50 |  |
| Group members discussed a few given options with NGO-provided experts, jointly selected one option, and finalised the proposal with the expert | 75 |  |
| Group members discussed all possible options with NGO-provided experts, short-listed a few options, jointly selected one option, and finalised the proposal with the expert | 100 |  |

Reasons for score

- GROUP DEVELOPMENT

4.1	What is the nature of group activities?

| OPTIONS | SCORES | SCORE |
| --- | --- | --- |
| Only saving; no loaning | 0 |  |
| Saving and loaning only for consumption purposes | 25 |  |
| From own savings, loaning without default for at least one productive purpose | 50 |  |
| Also bank loan | 75 |  |
| Also received funds from government development schemes | 100 |  |

Reasons for score

4.2	How much has the group developed? (fill in separately for CI and IG groups)

Social infrastructure group

| OPTIONS | SCORES | SCORE |
| --- | --- | --- |
| Has submitted for sub-project proposal | 0 |  |
| Sub-project funds sanctioned | 25 |  |
| Sub-project funds released | 35 |  |
| Also materials purchased | 40 |  |
| Construction work in progress | 45 |  |
| Construction work completed satisfactorily | 50 |  |
| O&M carried out regularly | 75 |  |
| New activity taken up by group | 100 |  |

Income generation group

| OPTIONS | SCORES | SCORE |
| --- | --- | --- |
| Has submitted for sub-project proposal | 0 |  |
| Sub-project funds sanctioned | 25 |  |
| Sub-project funds released | 35 |  |
| Also material purchased | 40 |  |
| Also working capital mobilised (e.g., a bank, or an SHG, etc.) | 45 |  |
| Sub-project activity started | 50 |  |
| Profits made from sub-project activity | 75 |  |
| Expansion of sub-project activity with profits | 100 |  |

Reasons for score

4.3	What is the nature of facilitation of group development?

| OPTIONS | SCORES | SCORE |
| --- | --- | --- |
| No facilitation; the CF has not visited the group since the sub project proposal was submitted | 0 |  |
| Some facilitation; CF comes but not regularly and does not provide all the required information | 25 |  |
| Average facilitation; CF comes regularly, gives all required information, and has taught them how to open bank accounts and to maintain account books | 50 |  |
| Good facilitation; In addition, all members know dates of CF’s visits, and know when awareness and training programmes are to be held | 75 |  |
| Excellent facilitation; In addition, CF has taught group how to get information from government offices and to resolve conflicts within the group | 100 |  |

Reasons for score

- CAPACITY BUILDING

Did members undergo training?		0. 	NO		Go to Question 6

1. 	YES		Continue

What was the focus of training		0.	Improving existing skills

1.	Building new skills

Details of training received

| Subject of Training | Year | No: attended | No: of days attended | Organised by? | Place of training |
| --- | --- | --- | --- | --- | --- |
| 1. |  |  |  |  |  |
| 2. |  |  |  |  |  |
| 3. |  |  |  |  |  |
| 4. |  |  |  |  |  |
| 5. |  |  |  |  |  |

## Comments and Observations

5.1	What was the nature of training opportunities?

| OPTIONS | SCORES | SCORE |
| --- | --- | --- |
| No relevant training was organised for the group | 0 |  |
| Training was organised but group members were not informed | 10 |  |
| Only a few key group members were informed, selected and sent | 25 |  |
| The whole group was informed, and members attended – but training not organised on the basis of the training needs assessment and all who wished to attend (especially women) were not helped to do so | 50 |  |
| Training organised according to the training needs assessment, the entire group was informed and members attended - but all those who wished to attend (especially women & poor) were not helped to do so | 75 |  |
| Training organised according to training needs assessment, the entire group was informed, and all who wished to attend (especially women & poor) were helped to do so | 100 |  |

Reasons for score

5.2	Was training effective?

| OPTIONS | SCORES | SCORE |
| --- | --- | --- |
| None of the trainees took the training seriously and did not learn anything | 0 |  |
| Even those who attended seriously could not learn much (e.g., badly organised, bad trainers, etc.) | 25 |  |
| All those who attended seriously learnt the skill sufficiently, are using it effectively | 50 |  |
| All those who attended the training learnt the skill sufficiently; and most are using it effectively | 75 |  |
| All those who attended the training learnt the skill sufficiently; and all are using it effectively | 100 |  |

Reasons for score

- PARTICIPATION IN DECISION-MAKING

6.1	What is the nature of decision-making within the group?

| OPTIONS | SCORES | SCORE |
| --- | --- | --- |
| Few members take all decisions, others do not speak up even when they have a problem | 0 |  |
| Few members take all decisions, others speak up when they have a problem, but cannot influence decisions | 25 |  |
| Few members take all decisions, others are able to influence decisions that affect them – but no such situation has come up so far | 40 |  |
| Few members take all decisions, but others have been able to influence at least one decision that affected them | 50 |  |
| Decisions are taken by majority rule, but some members are unhappy with decision | 75 |  |
| Decisions are taken by all by consensus (although every member has the right to say No) | 100 |  |

Reasons for score

6.2	What is the nature of women’s participation in mixed CIGs?

| OPTIONS | SCORES | SCORE |
| --- | --- | --- |
| Women are group members, but do not attend meetings | 0 |  |
| Women members attend meetings, but do not speak | 25 |  |
| Women members attend and speak and are able to influence decisions that affect them – but no such situation has come up so far | 40 |  |
| Women members speak up on issues concerning them, and have influenced at least one decision | 50 |  |
| Women members speak up even on some group issues and have influenced at least one group decision | 75 |  |
| Women members speak up on all group issues and influence decisions – just like men | 100 |  |

Reasons for score

- TRANSPARENCY

7.1	How accessible is project-related information to group members?

| OPTIONS | SCORES | SCORE |
| --- | --- | --- |
| Difficult, CF not available when needed to answer questions | 0 |  |
| Members can get the information from CF, but they do not always know when CF comes | 25 |  |
| Members know when CF comes and get all the information they need from the CF | 50 |  |
| In addition, even without asking, members are given information regularly in meetings | 75 |  |
| In addition, project information is put up on a board, which is accessible to all | 100 |  |

Reasons for score

Specific questions on sub-project

| TYPE OF ACTIVITY | Income Generation/Community Infrastructure/Land-based activity |
| --- | --- |
| NAME OF ACTIVITY |  |

Fill in whatever is relevant to the sub-project

1.	Components of sub-project proposed

|  | According To Group Members | According to Proposal | Sanctioned Amount |
| --- | --- | --- | --- |
| ### Total |  |  |  |
| Labour component |  |  |  |
| Materials (specify) |  |  |  |
| Others (specify) |  |  |  |

2.	Details of Labour

|  | According to Group Members | According to Proposal |
| --- | --- | --- |
| Total Labour Component |  |  |
| Amount per member (Total labour component / no: of members in group) |  |  |
| Hours of work per day (male) |  |  |
| Hours of work per day (female) |  |  |
| Daily wage (male) |  |  |
| Daily wage (female) |  |  |
| No: of days of work per member (male) (Amount per member/wage rate) |  |  |
| No: of days of work per member (female) (Amount per member/wage rate) |  |  |

3.	Details of Contribution

| Contribution per member | According to Group Members | According to Proposal |
| --- | --- | --- |
| ### Lump sum |  |  |
| By shramdaan |  |  |
| Per week |  |  |
| Per 15 days |  |  |

- Expected Returns per day and per month

(for non-land based income generating activities)

| ISSUE | QUANTITY | UNITS | PRICE per unit | RETURNS |
| --- | --- | --- | --- | --- |
| Expected production per day per person |  |  |  |  |
| Expected production per month per person |  |  |  |  |
| OR Days to produce 1 unit of output |  |  |  |  |

5.	Marketing

###### Current Situation

|  |  | PRICE GIVEN |  |  |
| --- | --- | --- | --- | --- |
|  |  | Rs. | UNIT |  |
| Market where they sell or expect to sell? | 1. LOCAL |  |  |  |
|  | 2. TALUK |  |  |  |
|  | 3. DISTRICT |  |  |  |
|  | 4. STATE |  |  |  |
|  | 5. OTHER |  |  |  |
| Name of market |  |  |  |  |
| Type of buyer | 1. VILLAGE AGENT |  |  |  |
|  | 2. MARKET BUYER |  |  |  |
|  | 3. NGO |  |  |  |
|  | 4. STATE AGENCY |  |  |  |
| Name of buyer |  |  |  |  |
| Reason for selling to this buyer |  |  |  |  |

Best Situation

| Where would they like to sell? |  |
| --- | --- |
| Who would they like to sell to? |  |
| Expected price? |  |
| Why are they not selling there now? |  |

6. Costs

|  | ###### AMOUNT SPENT | NO. OF UNITS | PRICE PER UNIT | Amount (Price x No:) | PURCHASE DETAILS |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | YEAR | PLACE | PERSON/AGENCY |
| Equipment |  |  |  |  |  |  |  |
| Type of equipment |  |  |  |  |  |  |  |
| Working capital |  |  |  |  |  |  |  |
| Type of material |  |  |  |  |  |  |  |
| Details of Transport costs |  |  |  |  |  |  |  |

How can costs be reduced?

Why are they not doing so?

What problems are they facing currently?

What suggestions do they have for future improvement?

7.	Details of Production (for land-based income-generating activities)

|  | According to Group Members | According to Proposal |
| --- | --- | --- |
| Proposed Vegetable crops |  |  |
| Proposed Area under different crops 1. 2. 3. 4. 5. 6. 7. |  |  |
| Ploughings per Bigha |  |  |
| Cost per Ploughing per Bigha |  |  |
| Pre-sowing fertiliser or manure application costs per Bigha |  |  |
| Seed or sapling Cost per Bigha per Bigha |  |  |
| No. of irrigation required |  |  |
| Cost per irrigation per Bigha |  |  |
| No. fertiliser or manure application during the crop |  |  |
| Fertiliser or manure application costs each time per Bigha |  |  |
| No. of Weeding required |  |  |
| Costs per Weeding per Bigha |  |  |
| No. of pesticide applications |  |  |
| Cost per pesticide application per Bigha |  |  |
| Harvesting costs per Bigha |  |  |
| Out put per bigha |  |  |
| Post harvest cleaning costs if any per Quintal |  |  |
| Special storage or packing costs per Quintal |  |  |
| Transport cost to the point of sale per Quintal |  |  |

How can costs be reduced?

Why are they not doing so?

What problems are they facing currently?

What suggestions do they have for future improvement?

| ENDING TIME |  | TOTAL TIME |  |
| --- | --- | --- | --- |

ANNEX 2

QPA Pilot in Churu and Dausa Districts: Main Findings

This Annex contains results from village assessments done in Ratangarh block of Churu district and Lalsot block in Dausa district, and the main points from the two district stakeholders’ meeting.

The village assessments are in two parts: (1) the secondary data collected from the villages on the number of poor, and (2) the scores from the QPA.

QPA PILOT IN CHURU DISTRICT

| VILLAGE ASSESSMENTS | CHURU DISTRICT Oct-01 |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Village Name | MOLLESAR |  |  | GHUMANDA & BACHRARA |  |  | DAUDSAR |  |  | GORISAR |  |  |
| Block | Ratangarh |  |  | Ratangarh |  |  | Ratangarh |  |  | Ratangarh |  |  |
| Date of Assessment | 16-Oct-01 |  |  | 16-Oct-01 |  |  | 18-Oct-01 |  |  | 18-Oct-01 |  |  |
| GENERAL VILLAGE INFORMATION | QPA | Avail. |  | QPA | Avail. |  | QPA | Avail. |  | QPA | Avail. |  |
|  | Survey | Stats. | Difference | Survey | Stats. | Difference | Survey | Stats. | Difference | Survey | Stats. | Difference |
| Population | 1000 | 705 | 295 | 3965 | 3206 | 759 | 6000 | 4254 | 1746 | 2466 | 1947 | 519 |
| Available Secondary Information | 705 |  |  |  |  |  |  |  |  |  |  |  |
| No: of households | 105 | 193 | 88 | 630 | 630 | 0 | 1000 | 841 | -159 | 415 | 396 | -19 |
| Available Secondary Information | 193 |  |  |  |  |  |  |  |  |  |  |  |
| BPL Families in the List | 67 | 68 |  | 195 | 195 |  | 230 | 230 |  | 145 | 145 |  |
| Poor families not in list | 10 |  |  | 18 |  |  | 50 |  |  | 50 |  |  |
| Families considered poor by villagers | 51 |  | -16 | 196 |  | 1 | 463 |  | 233 | 122 |  | -23 |
| Number of these poor in CIG groups | 32 |  |  | 28 |  |  | 42 |  |  | 15 |  |  |
| No: of CIGs | 3 |  |  | 3 |  |  | 3 |  |  |  |  |  |
| % of BPL families not in CIGs |  | 52% |  |  | 86% |  |  | 82% |  |  | 90% |  |

QPA PILOT IN CHURU DISTRICT

| GROUP ASSESSMENT | CHURU DISTRICT |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | MOLLESAR |  |  | GHUMANDA & BACHRARA |  |  | DAUDSAR |  |  | GORISAR |  |  |
|  | Ratangarh |  |  | Ratangarh |  |  | Ratangarh |  |  | Ratangarh |  |  |
|  | 16-Oct-01 |  |  | 16-Oct-01 |  |  | 18-Oct-01 |  |  | 18-Oct-01 |  |  |
| Name of Group | Jagruti | Pratap | Ambedkar | Sri Ganesh | Laxmi | Suraj | Ch.Ch. Singh | Ambedkar | Talaniya | Pratap | Azad | Ch.Ch.Singh |
| Type of Group (IG, CI, LB)* | LB | IG | CI | LB | IG | IG | LB | IG | IG | IG | IG | CI |
| Activity chosen | Kund Hort. | Brick mkg | School bldg | Kund Hort. | Carpet mkg | Kund Hort. | Kund Hort. | Poultry | Poultry | Poultry | Poultry | School bldg. |
| Total no: of members | 10 | 10 | 10 (2) | 11(1) | (10) | 7 | 15 | 10 | 10 | 10 | 10 | 10 |
| No: of members present | 9 | 5 | 10 (2) | 8(0) | (10) | 5 | 7 | 5 | 6 | 5 | 9 | 10 |
| 1. AWARENESS GENERATION |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.1 How does the project hope to reduce poverty? | 40 | 30 | 5 | 60 | 50 | 75 | 25 | 25 | 25 | 15 | 60 | 100 |
| 2. FORMATION OF GROUPS |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.1 How was the CIG formed? | 45 | 45 | 45 | 50 | 45 | 50 | 50 | 45 | 50 | 30 | 50 | 50 |
| 3. SUB-PROJECT PROPOSAL |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.1 What was the process of finalising the sub-project proposal? | 35 |  | 35 |  | 50 |  | 50 | 50 | 75 | 75 | 45 | 75 |
| 4. GROUP DEVELOPMENT |  |  |  |  |  |  |  |  |  |  |  |  |
| 4.1 What is the nature of group activities? | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| 4.2 How much has the group developed? | 0 |  | 0 |  | 25 |  |  |  |  | 0 | 0 | 0 |
| 4.3 What is the nature of facilitation of group development? | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 60 | 40 | 40 | 45 | 40 |
| 5. CAPACITY BUILDING |  |  |  |  |  |  |  |  |  |  |  |  |
| 5.1 Did members undergo training? | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO |
| 5.2 What was the nature of training opportunities? |  |  |  |  |  |  |  |  |  |  |  |  |
| 5.3 Was training effective? |  |  |  |  |  |  |  |  |  |  |  |  |
| 6. PARTICIPATION IN DECISION-MAKING |  |  |  |  |  |  |  |  |  |  |  |  |
| 6.1 What is the process of decision-making within the group? | 85 | 80 | 100 | 85 | 100 | 90 | 80 | 85 | 80 | 50 | 85 | 100 |
| 6.2 What is the nature of women's participation in mixed CIGs? | N.A. |  | 90 | 0 |  |  |  |  |  |  |  |  |
| 7. TRANSPARENCY |  |  |  |  |  |  |  |  |  |  |  |  |
| 7.1 How accessible is project-related information to group members? | 40 | 30 | 40 | 75 | 75 | 75 | 75 | 50 | 75 | 75 | 75 | 75 |

* IG: Income Generation; CI = Community Infrastructure; LB = Land based activities

# Points from the Churu District Stakeholder Meeting (20 October 2001, DPMU Office, Churu)

| ISSUES CONCERNING | ISSUE | SPECIFIC CAUSE OF THE PROBLEM | LEVEL AT WHICH ACTION IS NECESSARY | DECISION TAKEN AT SHM | OTHER INFORMATION |
| --- | --- | --- | --- | --- | --- |
| Community Facilitators | CFs facing hostility and distrust from villagers | Promises of quick implementation not fulfilled (initially told within 3 months, then additional months – now its more than 12 months with no work done) | SPMU – to clarify issues that are hampering approval of sub-projects: change of registration of land in the name of the CIG required for land-based projects | DPM to personally go with 5 CFs and try and convince villagers to sign over their private land to the CIG | Apparently this has been done in Dholpur; but there is no confirmation of this. Basically, there are lots of family members, some living elsewhere, who need to sign in order to transfer land. |
|  | Salary not paid for 6 months+ | NGO contract specifies quarterly payment – which implies that even normal payments will take around 5 months | SPMU – NGO needs to re-negotiate its contract to ensure that payments are quarterly | NGO to look into contracting | SPMU clarified that a decision has already been taken to make payments monthly |
|  | TA not paid for 6 months+ | Again, NGO contract specifies quarterly settlement | SPMU – NGO | NGO to look into contracting | DPM Churu mentioned that a system of 75% advance payment could be worked out – as is done in govt. corporations |
|  | Materials needed for CFs to work, including chair/table, durrie, torch, etc. | NGO has contracted to provide Rs. 15,000 per CF, out of which these items can be provided – but this has not been done yet. | NGO | NGO to look into using this amount |  |
|  | Training provided was general (field experience has taught them more), but the need more information on new areas of training (e.g., account keeping, sub-project preparation, book keeping, cash flow analysis, project objectives and scope, etc.) retraining necessary | Training institution did not provide all the information necessary to facilitate CF’s working in the field. | SPMU/NGO – to direct Training organisation to provide additional training, specific to DPIP and to CF’s practical needs on the field. | Issue to be raised with SPMU |  |
|  | CFs need to involve CIGs more in the planning of sub-project proposals | CF’s do not have sufficient training or access to training resources to involve CIGs more. | SPMU/NGO – to direct Training organisation to provide better training | Issue to be raised with SPMU |  |
|  | Recruiting and retaining women CFs is a problem | No conveyance provided to enable women to work effectively | SPMU – NGO – to make a special provision in the contract | Issue to be raised with SPMU |  |
|  | Insecurity of tenure | CFs contracted by NGO only for 10 months initially | SPMU – NGO | Issue to be raised with SPMU |  |
| District Project Coordinator | Provision of exposure visits and training for the CIGs prior to sub-project proposal formulation | The Guidelines of the SPMU do not provide for such prior action and expenditure | SPMU – in terms of a change in the guidelines | Issue to be raised with SPMU |  |
|  | Costs budgeted for CIG formation (Rs. 1000 per village – irrespective of the number of CIGs formed) is a disincentive against forming more than 1 CIG per village | SPMU-NGO contract has this as a budgetary condition. | SPMU/NGO | Issue to be raised with SPMU |  |
|  | Working with 1 year planning horizon | SPMU Guidelines suggest that CFs must complete sub-projects in 1 year & move to next village | SPMU | Issue to be raised with SPMU | The PAD does not mention 1 year, but the phasing table in the PIP suggests this |
| NGO | Provision of experts | NGO contract provides too little remuneration and too small a time span to get good experts | SPMU – NGO to re-examine contract | Collector offered to provide experts – needs to be raised with the SPMU |  |
|  | Check on experts work | No provision for ‘master experts’ | SPMU | Issue to be raised with SPMU | Sub-sectoral orientation would be useful. |
|  | Lack of awareness of ‘process and learning’ nature of project | Project documents specifying this (e.g., (PAD)) not circulated initially to district level staff (only in Sep 2001) | SPMU – orientation training necessary for project staff | Issue to be discussed with SPMU |  |
| District Project Management Unit | Clarity on roles and responsibilities | SPMU has not shared enough information on this aspect | SPMU | Issue to be raised with SPMU |  |
|  | Inadequate staffing system | Need assistants to each District Manager; change of status of DPM to General Manager (district) | SPMU | Issues to be raised with SPMU |  |
|  | Billing system is unnecessarily complicated | Designed without taking into account better existing govt. systems | SPMU | Issue to be raised with SPMU |  |

QPA PILOT IN DAUSA DISTRICT

| VILLAGE CIG ASSESSMENT | DAUSA October 2001 |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Village Name | Kushalpura |  |  | Nichuniyan |  |  | Sindoli |  |  | Kanwarpura |  |  |
| Block | Lalsot |  |  | Lalsot |  |  | Lalsot |  |  | Lalsot |  |  |
| Date of Assessment | 9-Oct-01 |  |  | 10/112001 |  |  | 9-Oct-01 |  |  | 11-Oct-01 |  |  |
| GENERAL VILLAGE INFORMATION | QPA | Avail |  | QPA | Avail |  | QPA | Avail |  | QPA | Avail |  |
|  | Survey | Stats. | Difference | Survey | Stats. | Difference | Survey | Stats. | Difference | Survey | Stats. | Difference |
| Population | 1500 | 917 | 583 | 1200 | 674 | 526 | 1800 | 915 | 885 | 2000 | 484 | 1516 |
| % increase in population | 64% |  |  | 78% |  |  | 97% |  |  | 313% |  |  |
| No: of households | 110 |  |  | 150 |  |  | 240 |  |  | 250 |  |  |
| BPL Families in the List | 103 |  |  | 75 |  |  | 121 |  |  | 175 |  |  |
| Poor families not in list | 10 |  |  | 23 |  |  | 34 |  |  | 29 |  |  |
| Families considered poor by villagers |  |  |  |  |  |  |  |  |  |  |  |  |
| Number of these poor in CIG groups | 33 |  |  | 39 |  |  | 22 |  |  | 28 |  |  |
| No: of CIGs | 3 |  |  | 3 |  |  | 2 |  |  | 3 |  |  |
| % of BPL families not in CIGs | 68% |  |  | 48% |  |  | 82% |  |  | 84% |  |  |

QPA PILOT IN DAUSA DISTRICT

| GROUP ASSESSMENT | DAUSA October 2001 |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Village Name | Kushalpura |  |  | Nichuniyan |  |  | Sindoli |  |  | Kanwarpura |  |  |
| Block | Lalsot |  |  | Lalsot |  |  | Lalsot |  |  | Lalsot |  |  |
| Date of Assessment | 9-Oct-01 |  |  | 10/112001 |  |  | 9-Oct-01 |  |  | 11-Oct-01 |  |  |
| Name of Group | Bajrangi | Maurya |  | Jai Hanuman | Jai Shankar | Sri Mathari | Vikas | Ujala |  | Jai Hanuman | Jai Bhomiya |  |
| Type of Group (IG, CI, LB) | LB | IG | CI | LB | LB | IG | IG | IG |  | LB | LB | CI |
| Activity chosen | Vegetable | Shoe-mkg | Sch. Bldg | Vegetable | Vegetable | Dairy | Dairy | Kashida |  | Vegetable | Vegetable | Handpump |
| Total no: of members | 13 | 10 | 10 | 14 | 15 | 10 | 12 | 10/9 |  | 13 | 15 |  |
| No: of members present | 3 | 4 | 4 | 5 | 4 | 6 |  |  |  |  |  |  |
| 1. AWARENESS GENERATION |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.1 How does the project hope to reduce poverty? | 60 | 60 | 60 | 35 | 40 | 50 | 45 | 35 |  | 50 | 65 |  |
| 2. FORMATION OF GROUPS |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.1 How was the CIG formed? | 50 | 50 | 50 | 20 | 40 | 50 | 50 | 50 |  | 50 | 45 |  |
| 3. SUB-PROJECT PROPOSAL |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.1 What was the process of finalising the sub-project proposal? | 75 | 40 | 50 | 0 | 75 | 35 | 75 | 40 |  | 75 | 100 |  |
| 4. GROUP DEVELOPMENT |  |  |  |  |  |  |  |  |  |  |  |  |
| 4.1 What is the nature of group activities? | 50 | 50 | 50 | 25 | 70 | 65 | 25 | 35 |  | 65 | 70 |  |
| 4.2 How much has the group developed? | 35 | 0 | 40 | 0 | 25 | 40 | 35 | 25 |  | 20 | 20 | 45 |
| 4.3 What is the nature of facilitation of group development? | 40 | 35 | 35 | 35 | 35 | 35 | 35 | 35 |  | 65 | 45 |  |
| 5. CAPACITY BUILDING |  |  |  |  |  |  |  |  |  |  |  |  |
| 5.1 Did members undergo training? | NO | NO | NO | NO | YES | YES | YES | NO |  | NO | Yes | NO |
| 5.2 What was the nature of training opportunities? |  |  |  |  | 35 | 20 | 50 |  |  |  | 50 |  |
| 5.3 Was training effective? |  |  |  |  | 25 | 25 | 25 |  |  |  | 25 |  |
| 6. PARTICIPATION IN DECISION-MAKING |  |  |  |  |  |  |  |  |  |  |  |  |
| 6.1 What is the process of decision-making within the group? | 100 | 100 | 100 | 45 | 100 | 70 | 100 | 80 |  | 100 | 100 |  |
| 6.2 What is the nature of women's participation in mixed CIGs? | NA | NA | 40 | NA | 100 | NA | 25 | NA |  | 75 | NA |  |
| 7. TRANSPARENCY |  |  |  |  |  |  |  |  |  |  |  |  |
| 7.1 How accessible is project-related information to group members? | 80 | 75 | 75* | 40 | 40 | 75 | 75 | 75 |  | 75 | 75 |  |

# * IG: Income Generation; CI = Community Infrastructure; LB = Land based activities

# Points from the Dausa District Stakeholder Meeting (13 October 2001, Collectorate Bulding, Dausa )

| ISSUES CONCERNING | ISSUE | SPECIFIC CAUSE OF THE PROBLEM | LEVEL AT WHICH ACTION IS NECESSARY | DECISION TAKEN AT SHM | OTHER INFORMATION |
| --- | --- | --- | --- | --- | --- |
| Community Facilitators | CFs facing hostility and distrust from villagers | Villagers feel the project will not deliver, since it is more than a year since CIGs were formed with the promise of quick action. | Banks – to specify conditions under which the loans can be given; DPMU – to clarify to the bank how CIGs are like SHGs, but that the CFs are unique to CIGs | Bank to provide working capital for buffalo purchase to 2 groups initially; rest to go outside district to purchase Awareness building workshop to be arranged by DPMU with banks and CFs; |  |
|  | Salary not paid for 6 months+ | NGO contract specifies quarterly payment – which implies that even normal payments will take around 5 months | SPMU – NGO needs to re-negotiate its contract to ensure that payments are quarterly | NGO to look into contracting | SPMU clarified that a decision has already been taken to make payments monthly |
|  | TA not paid for 6 months+ | Again, NGO contract specifies quarterly settlement | SPMU – NGO | NGO to look into contracting | DPM Churu mentioned that a system of 75% advance payment could be worked out – as is done in govt. corporations |
|  | Materials needed for CFs to work, including chair/table, durrie, torch, etc. | NGO has contracted to provide Rs. 15,000 per CF, out of which these items can be provided – but this has not yet been done. | NGO | NGO to look into using this amount |  |
|  | Training provided was general (field experience has taught them more), but the need more information on new areas of training (e.g., account keeping, sub-project preparation, book keeping, cash flow analysis, project objectives and scope, etc.) retraining necessary | Training institution did not provide all the information necessary to facilitate CF’s working in the field. | SPMU/NGO – to direct Training organisation to provide additional training, specific to DPIP and to CF’s practical needs on the field. | Issue to be discussed with SPMU |  |
|  | CFs need to involve CIGs more in the planning of sub-project proposals | CF’s do not have sufficient training or access to training resources to involve CIGs more. | SPMU/NGO – to direct Training organisation to provide better training | Issue to be discussed with SPMU |  |
|  | More team spirit and less hierarchy in the office | Working environment provided by NGO staff and DPC | NGO | To be discussed with the NGO later |  |
| District Project Coordinator | Salary of experts not paid (Dr. Rawat, Animal Husbandry, and the PRA expert) | NGO/DPC did not send in written confirmation of the date of hiring of the expert – required by DPMU to calculate period of payment | SPMU – since the rules have been framed at their level | Issue to be discussed with SPMU | SPMU clarified that a decision had been taken at the SPMU to release the outstanding amount |
|  | Provision of exposure visits and training for the CIGs prior to sub-project proposal formulation | The Guidelines of the SPMU do not provide for such prior action and expenditure | SPMU – in terms of a change in the guidelines | Issue to be discussed with SPMU |  |
|  | Costs budgeted for CIG formation (Rs. 1000 per village – irrespective of the number of CIGs formed) is a disincentive against forming more than 1 CIG per village | SPMU-NGO contract has this as a budgetary condition. | SPMU/NGO | Issue to be discussed with SPMU |  |
|  | Shifting of the DPCs office to the Collectorate building, to reduce time taken to liase with DPMU staff and Line Departments | No explicit stipulation in Guidelines or NGO contract | District administration | Collector willing to provide as much space as necessary. DPC willing to move provided given room 210, or a room similar in size – Collector said he would look into it |  |
|  | Working with 1 year planning horizon | SPMU Guidelines suggest that CFs must complete sub-projects in 1 year & move to next village | SPMU | Issue to be raised with SPMU | The PAD does not mention 1 year, but the phasing table in the PIP suggests this |
| NGO | Provision of experts | NGO contract provides too little remuneration and too small a time span to get good experts | SPMU – NGO to re-examine contract | Collector offered to provide experts – needs to be raised with the SPMU |  |
|  | Check on experts work | No provision for ‘master experts’ | SPMU | Issue to be discussed with SPMU | Sub-sectoral orientation would be useful. |
|  | Lack of awareness of ‘process and learning’ nature of project | Project documents specifying this (e.g., Project Appraisal Document (PAD)) not circulated initially to district level project staff (only done in September 2001) | SPMU – orientation training necessary for project staff | Issue to be discussed with SPMU |  |
| District Project Management Unit | Clarity on roles and responsibilities | SPMU has not shared enough information on this aspect | SPMU | Issue to be discussed with SPMU |  |
| District Collector | Dovetailing of other government schemes with DPIP | Little encouragement from SPMU to letter written by the Collector urging such dovetailing? | SPMU – in terms of explicit permission and support for dovetailing | Issue to be discussed with SPMU |  |
|  |  |  |  | Collector to arrange to provide details of available schemes and programmes for the rural poor to the DPC/CFs. | A similar exercise to compile schemes being run by all line departments has been initiated by the SPMU in September 2001 |

From the internal note on ‘Quantified Participatory Assessments for DPIP’ summarising discussions  between A. J. James and Nirmala Murty, Bangalore, 5th May 2001.

A key secondary statistic collected is the number of poor in the village as identified by the villagers themselves, which is often a different number than that given in the BPL list. In addition, information was collected on all the key indicators used to identify and rank districts, blocks and villages, including the access of the poor to economic and social infrastructure, and services, cropping statistics and water quality. The purpose of collecting this information is to update existing secondary information, since existing secondary data from the Census of 1991 is dated, and the results of the current census are not yet available. Moreover, regular collection of these statistics will provide a more detailed look at project progress over time and a better guide to end line status (where the Census of 2001 may be the only major benchmark available to gauge change in these secondary statistics over the project period).

These questions and options were revised during the pre-test so that they elicited meaningful answers. For example, while the obvious question to understand the impact of the process of awareness generation carried out may be to ask ‘What do you think is the aim of the project?’, this elicited a uniform but unhelpful response - ‘To reduce poverty’. Therefore, the question was changed to the present, to try and understand whether the CFs had informed the group about all the various dimensions of project activities and impact (e.g., saving and loaning, capacity building to improve access to social and economic infrastructure, etc.). Note that the final option corresponds to the first objective of the project – ‘Mobilize and empower the poor and help them to develop strong grassroots organisations that facilitate access to and participation in democratic and development processes’

At the state-level stakeholders meeting, the District Project Manager of Dausa reported that, following the decision taken at the district stakeholders meeting, one dairy group had been lent working capital by the concerned bank, and another would receive its loan shortly.

It is assumed here that the project will support each CIG for three years.

See section 2.4.1 for a discussion on assessing project processes in terms of activities and outcomes.

The numbers in this and the following tables are prefixed by the number of the year. Thus the issue numbered 3.2 refers to Year 3 issue 2.